## CRL_IEC62443_Checklist_Complete
Category | Criticality | Artifact_ID | Artifact_Name | IEC_62443_Reference | Responsible_Party | Action | Lifecycle_Phase | Handover_Status | Related_Standards | Status | Due_Date | Completed_Date | Notes
CSMS |  | CSMS-001 | Cybersecurity Management System (CSMS) | IEC 62443-2-1 | Integrator |  | Program Management | Not Handed Over - AT Establishes | ISO 27001
CSMS |  | CSMS-002 | CSMS Security Policy | IEC 62443-2-1 SR 1.1 | Integrator |  | Program Management | Not Handed Over - AT Creates | ISO 27001
CSMS |  | CSMS-003 | Organizational Structure and Responsibilities | IEC 62443-2-1 SR 1.2 | Integrator |  | Program Management | Not Handed Over - AT Defines | ISO 27001
CSMS |  | CSMS-004 | Risk Management Process | IEC 62443-2-1 SR 2.3 | Integrator |  | Program Management | Not Handed Over - AT Ongoing | ISO 27005
CSMS |  | CSMS-005 | Incident Response Plan | IEC 62443-2-1 SR 2.9 | Operator (AT) |  | Program Management | Not Handed Over - AT Executes | NIST SP 800-61
CSMS |  | CSMS-006 | Business Continuity / Disaster Recovery Plan | IEC 62443-2-1 SR 2.10 | Operator (AT) |  | Program Management | Not Handed Over - AT Maintains | ISO 22301
CSMS |  | CSMS-007 | Security Training Program | IEC 62443-2-1 SR 2.7 | Operator (AT) |  | Program Management | Not Handed Over - AT Trains | ISO 27001
CSMS |  | CSMS-008 | Third-Party Risk Management | IEC 62443-2-1 SR 2.4 | Operator (AT) |  | Program Management | Not Handed Over - AT Manages | ISO 27036
ZCR - Zone & Conduit Risk |  | ZCR-001 | System Under Consideration (SuC) Definition | IEC 62443-3-2 ZCR 1 | Joint (Integrator and Operator) | Consensus of parties | Risk Assessment | HANDOVER - Joint Development | ISO 15288
ZCR - Zone & Conduit Risk |  | ZCR-002 | Asset Inventory and Registry | IEC 62443-3-2 ZCR 1 | Integrator | Integrator Hand to Operator | Risk Assessment | HANDOVER - Integrator Creates | CISA OT Guide
ZCR - Zone & Conduit Risk |  | ZCR-003 | High-Level Risk Assessment | IEC 62443-3-2 ZCR 2 | Integrator | Integrator Hand to Operator | Risk Assessment | HANDOVER - Integrator Initiates | ISO 27005
ZCR - Zone & Conduit Risk |  | ZCR-004 | Zone and Conduit Partitioning | IEC 62443-3-2 ZCR 3 | Integrator | Integrator Hand to Operator | Risk Assessment | HANDOVER - Critical Design | CLC TS 50701
ZCR - Zone & Conduit Risk |  | ZCR-005 | Zone Definitions and Specifications | IEC 62443-3-2 ZCR 3 | Integrator | Integrator Hand to Operator | Risk Assessment | HANDOVER | EN 50129
ZCR - Zone & Conduit Risk |  | ZCR-006 | Conduit Definitions and Specifications | IEC 62443-3-2 ZCR 3 | Integrator | Integrator Hand to Operator | Risk Assessment | HANDOVER | EN 50159
ZCR - Zone & Conduit Risk |  | ZCR-007 | Network Architecture Diagrams | IEC 62443-3-2 ZCR 3 | Integrator | Integrator Hand to Operator | Design/Risk | HANDOVER - Integrator Creates | ISO 27033
ZCR - Zone & Conduit Risk |  | ZCR-008 | Detailed Risk Assessment per Zone/Conduit | IEC 62443-3-2 ZCR 5 | Integrator | Integrator Hand to Operator | Risk Assessment | HANDOVER - Integrator Delivers | NIST SP 800-30
ZCR - Zone & Conduit Risk |  | ZCR-009 | Security Level Target (SL-T) Determination | IEC 62443-3-2 ZCR 4/5 | Integrator | Integrator Hand to Operator | Risk Assessment | HANDOVER - Joint Agreement | CLC TS 50701
ZCR - Zone & Conduit Risk |  | ZCR-010 | Cybersecurity Requirements Specification (CRS) | IEC 62443-3-2 ZCR 6 | Integrator | Integrator Hand to Operator | Requirements | HANDOVER - Critical Reference | EN 50129/50159
SYS - System Implementation |  | SYS-001 | System Security Plan (SSP) | IEC 62443-3-3 | Integrator | Integrator Hand to Operator | Design/Implementation | HANDOVER | NIST SP 800-18
SYS - System Implementation |  | SYS-002 | Network Segmentation Design | IEC 62443-3-3 SR 5.1 | Integrator | Integrator Hand to Operator | Design/Implementation | HANDOVER with Configs | ISO 27033
SYS - System Implementation |  | SYS-003 | Firewall Rules and ACLs | IEC 62443-3-3 SR 5.1/5.2 | Integrator | Integrator Hand to Operator | Implementation | HANDOVER - Config Backup | CIS Controls
SYS - System Implementation |  | SYS-004 | Identity and Access Management (IAM) Design | IEC 62443-3-3 SR 1.1-1.13 | Integrator | Integrator Hand to Operator | Design/Implementation | HANDOVER - AT Manages Users | ISO 27001 A.9
SYS - System Implementation |  | SYS-005 | Logging and Monitoring Configuration | IEC 62443-3-3 SR 3.3 | Integrator | Integrator Hand to Operator | Implementation | HANDOVER - AT Monitors | NIST SP 800-92
SYS - System Implementation |  | SYS-006 | Security Test Plan and Results | IEC 62443-3-3 | Integrator | Integrator Hand to Operator | Testing/Commissioning | HANDOVER - Evidence | NIST SP 800-115
SYS - System Implementation |  | SYS-007 | Integration Test Results | IEC 62443-3-3 | Integrator | Integrator Hand to Operator | Testing/Commissioning | HANDOVER | ISO 15288
SYS - System Implementation |  | SYS-008 | Cybersecurity Configuration Baselines | IEC 62443-3-3 SR 7.6 | Integrator | Integrator Hand to Operator | Implementation | HANDOVER - AT Change Mgmt | CIS Benchmarks
SYS - System Implementation |  | SYS-009 | Backup and Recovery Procedures | IEC 62443-3-3 SR 7.3 | Integrator | Integrator Hand to Operator | Implementation | HANDOVER - AT Executes | ISO 27001 A.12.3
SYS - System Implementation |  | SYS-010 | Patch Management Procedures | IEC 62443-3-3 SR 3.2 | Integrator | Integrator Hand to Operator | Operations | HANDOVER - AT Ongoing | ISO 27002
COMP - Components |  | COMP-001 | Component Security Capability Declarations | IEC 62443-4-2 | Integrator | Integrator Hand to Operator | Procurement/Design | HANDOVER - Asset Mgmt | ISASecure
COMP - Components |  | COMP-002 | Component Vulnerability Disclosures | IEC 62443-4-2 | Integrator | Integrator Hand to Operator | Procurement/Ops | HANDOVER - AT Monitors | NIST NVD
COMP - Components |  | COMP-003 | Software Bill of Materials (SBOM) | IEC 62443-4-1 SR 4.1 | Integrator | Integrator Hand to Operator | Dev/Procurement | HANDOVER - Vuln Mgmt | NTIA SBOM
DEV - Development |  | DEV-001 | Secure Development Lifecycle (SDL) Documentation | IEC 62443-4-1 | Integrator (if custom code) |  | Development | HANDOVER if applicable | ISO 27034
DEV - Development |  | DEV-002 | Security Requirements Traceability Matrix | IEC 62443-4-1 SR 1.1 | Integrator to Operator | Integrator Hand to Operator | Development | HANDOVER | ISO 26262
DEV - Development |  | DEV-003 | Threat Model and Attack Scenarios | IEC 62443-4-1 SR 1.2 | Integrator to Operator | Integrator Hand to Operator | Development/Design | HANDOVER | STRIDE, MITRE
SEC-CASE - Security Case | Critical | SEC-CASE-001 | CRL Cybersecurity Case | IEC 63452 / CLC TS 50701 | Integrator to Operator | Integrator Hand to Operator | Assurance | PRIMARY HANDOVER - Security Acceptance | EN 50129, UK NPSA
SEC-CASE - Security Case | Critical | SEC-CASE-002 | Security Assurance Report (SAR) | CLC TS 50701 / IEC 63452 | Integrator to Operator | Integrator Hand to Operator | Assurance | HANDOVER - Part of Case | ISO 15026
SEC-CASE - Security Case) | Critical | SEC-CASE-003 | Independent Security Assessment Report | CLC TS 50701 | Third-Party | Third Party Hand to Operator | Assurance | HANDOVER - Part of Case | EN 50129 ISA
SEC-CASE - Security Case | Critical | SEC-CASE-004 | Residual Risk Register | IEC 62443-3-2 | Integrator | Integrator Hand to Operator | Risk Assessment | CRITICAL - AT Must Accept | ISO 31000
SEC-CASE - Security Case | Critical | SEC-CASE-005 | Security Assumptions and Dependencies | IEC 62443-3-3 / CLC TS 50701 | Integrator | Integrator Hand to Operator | Assurance | CRITICAL - AT Must Maintain | EN 50129
HAND - Handover Plan | Critical | HAND-001 | CRL Cybersecurity Handover Plan | IEC 63452 / ISO 15288 | Integrator | Integrator Hand to Operator | Handover | PRIMARY HANDOVER - Master Plan | ISO 15288, CLC TS 50701
HAND - Handover Plan | Critical | HAND-002 | Operational Security Procedures for AT | IEC 62443-2-1 | Integrator develops - AT executes | Integrator Hand to Operator | Handover/Operations | HANDOVER - AT SOPs | ISO 27001
HAND - Handover Plan | Critical | HAND-003 | Maintenance Security Procedures | IEC 62443-3-3 SR 3.2 | Integrator develops - AT executes | Integrator Hand to Operator | Handover/Operations | HANDOVER | ISO 27002
HAND - Handover Plan | Critical | HAND-004 | Security Training Materials for AT Personnel | IEC 62443-2-1 SR 2.7 | Integrator develops - AT uses | Integrator Hand to Operator | Handover | HANDOVER - Training | ISO 27001
HAND - Handover Plan | Critical | HAND-005 | Security Monitoring and Alerting Configuration | IEC 62443-3-3 SR 3.3 | Integrator configures - AT monitors | Integrator Hand to Operator | Handover | HANDOVER - SOC Integration | NIST SP 800-137
HAND - Handover Plan | Critical | HAND-006 | Vendor Contact List and Support Contracts | IEC 62443-2-1 SR 2.4 | Integrator to Operator | Integrator Hand to Operator | Handover | HANDOVER | ISO 27036
HAND - Handover Plan | Critical | HAND-007 | Configuration Management Database (CMDB) Handover | IEC 62443-3-3 SR 7.6 | Integrator to Operator | Integrator Hand to Operator | Handover | HANDOVER - Live DB Transfer | ITIL
HAND - Handover Plan | Critical | HAND-008 | As-Built Documentation Package | IEC 62443-3-3 | Integrator to Operator | Integrator Hand to Operator | Handover | HANDOVER - Final Configs | ISO 15288
HAND - Handover Plan | Critical | HAND-009 | Security Performance Metrics and KPIs | IEC 62443-2-1 SR 2.11 | Integrator Establishes - AT measures | Integrator Hand to Operator | Handover | HANDOVER | ISO 27004
HAND - Handover Plan | Critical | HAND-010 | Incident Response Playbooks | IEC 62443-2-1 SR 2.9 | Integrator Develops - AT executes | Integrator Hand to Operator | Handover | HANDOVER - IR Procedures | NIST SP 800-61
HAND - Handover Plan | Critical | HAND-011 | Commissioning Test Results and Acceptance Criteria | IEC 62443-3-3 | Integrator to Operator | Integrator Hand to Operator | Commissioning/Handover | HANDOVER - Proof of Acceptance | ISO 15288
HAND - Handover Plan | Critical | HAND-012 | Lessons Learned and Recommendations | IEC 62443-2-1 SR 2.11 | Integrator to Operator | Integrator Hand to Operator | Handover | HANDOVER | ISO 27001
OPS - Ongoing Operations |  | OPS-001 | Annual Security Risk Re-assessment | IEC 62443-2-1 SR 2.3 | Operator (AT) | Operator Executes | Operations | Not Handed Over - AT Creates Annually | ISO 27005
OPS - Ongoing Operations |  | OPS-002 | Security Audit Logs and Reports | IEC 62443-3-3 SR 3.3 | Operator (AT) | Operator Executes | Operations | Not Handed Over - AT Generates | ISO 27001 A.12.4
OPS - Ongoing Operations |  | OPS-003 | Security Incident Records | IEC 62443-2-1 SR 2.9 | Operator (AT) | Operator Executes | Operations | Not Handed Over - AT Creates | ISO 27035
OPS - Ongoing Operations |  | OPS-004 | Patch Management Records | IEC 62443-3-3 SR 3.2 | Operator (AT) | Operator Executes | Operations | Not Handed Over - AT Maintains | ISO 27002
OPS - Ongoing Operations |  | OPS-005 | Change Management Records | IEC 62443-2-1 SR 2.5 | Operator (AT) | Operator Executes | Operations | Not Handed Over - AT Maintains | ITIL
OPS - Ongoing Operations |  | OPS-006 | Security Training Records | IEC 62443-2-1 SR 2.7 | Operator (AT) | Operator Executes | Operations | Not Handed Over - AT Maintains | ISO 27001
OPS - Ongoing Operations |  | OPS-007 | Vendor Security Assessment Results | IEC 62443-2-1 SR 2.4 | Operator (AT) | Operator Executes | Operations | Not Handed Over - AT Conducts | ISO 27036
OPS - Ongoing Operations |  | OPS-008 | Security Metrics Dashboard | IEC 62443-2-1 SR 2.11 | Operator (AT) | Operator Executes | Operations | Not Handed Over - AT Operates | ISO 27004
COMP-REG - Compliance |  | COMP-REG-001 | NIS2 Compliance Documentation (if applicable) | NIS2 Directive | Operator (AT) | Operator Executes | Compliance | Not Handed Over - AT Responsibility | EU NIS2
COMP-REG-002 |  | COMP-REG-002 | Rail Safety National Law (RSNL) Cybersecurity Integration | RSNL (NZ) | Operator (AT) | Operator Executes | Compliance | Not Handed Over - AT SMS | RSNL, ISO 45001
COMP-REG - Compliance |  | COMP-REG-003 | Insurance Requirements Compliance | Insurance Policy | Operator (AT) | Operator Executes | Compliance | Not Handed Over - AT Responsibility | Insurance Policy