## Status 27-Oct-2025
Executive Summary KPIs
Total Artifacts | 121
Complete | 9
Incomplete | 112

## CRL_62443_Cyber_Artifact_List
ID | Lifecycle_Phase | Target Completion Date | Complete | Notes | Responsible Party | Deliverable | Category | Artifact_ID | Artifact_Name | IEC_62443_Reference | Criticality_Level | RACI_Responsible_Org | RACI_Accountable_Org | RACI_Consulted_Org | RACI_Informed_Org | Responsibility_Description | Handover_Party | Acceptance_Activity | Acceptance_Criteria | Deliverable_Format | Related_Standards | Status | Target_Timeline | Dependencies | Notes2 | Column1 | Column2
1 | Pre-Project | 2025-10-10 | Yes | Not Provided, but CBN Risk Assessment lists defintitions (Consequences) and Risk ratings. NCC will use these. | AT | Risk Assessment Methodology | Asset Owner IACS Program | AO-2-1-001 | IACS Security Program Establishment | IEC 62443-2-1 | High | Asset Owner (AT) | Asset Owner (AT) |  |  | Asset Owner (AT) - Establishes | Not Handed Over - AT Internal Program | N/A - AT internal governance | AT Security Program per IEC 62443-2-1 established before project | Program Documentation | ISO 27001 | Incomplete | Before Project Starts | None | Per IEC 62443-2-1: Asset Owner (AT) MUST establish their organizational Security Program BEFORE the Automation Solution lifecycle begins.
2 | Pre-Project | 2025-10-10 | Yes | AT did not provide standards or poliocies, so addressed in MR (we are determining controls by IEC62443 Risk Process | AT | Risk Assessment Methodology | Asset Owner IACS Program | AO-2-1-002 | IACS Security Policies | IEC 62443-2-1 | High | Asset Owner (AT) | Asset Owner (AT) |  |  | Asset Owner (AT) - Establishes | Not Handed Over - AT Internal Program | N/A - AT internal governance | Security policies for IACS established by AT, approved by management, and communicated. | Policy Documents | ISO 27001 | Incomplete | Before Project Starts | AO-2-1-001 | AT establishes IACS-specific security policies per IEC 62443-2-1.
3 | Pre-Project | 2025-10-10 | Yes | NCC to Use IEC-62443 w/TS50701 (Rail standards) alignment | NCC | Risk Assessment Methodology | Asset Owner IACS Program | AO-2-1-003 | Risk Assessment Methodology | IEC 62443-2-1 SR 2.3 | High | Asset Owner (AT) | Asset Owner (AT) |  |  | Asset Owner (AT) - Establishes | Not Handed Over - AT Internal Program | N/A - AT internal governance | Risk assessment methodology defined for IACS, including consequence, likelihood, and risk tolerance. | Procedure Document | ISO 27005, ISO 31000 | Incomplete | Before Project Starts | AO-2-1-001 | AT defines HOW risk will be assessed. This is a critical input for the SI (Link Alliance).
4 | Pre-Project | 2025-10-10 | Yes | NCC to Use IEC-62443 w/TS50701 (Rail standards) alignment | NCC | Target Security Levels (SL-T) Defintion | Asset Owner IACS Program | AO-2-1-004 | Target Security Levels (SL-T) Definition | IEC 62443-3-2 | High | Asset Owner (AT) | Asset Owner (AT) |  |  | Asset Owner (AT) - Defines | Not Handed Over - AT Internal Program | N/A - AT internal governance | Asset Owner defines the organizational risk tolerance and target security levels (SL-T) for IACS zones. | Policy / Standard | NIST SP 800-82, IEC 62443-3-2 | Incomplete | Before Project Starts | AO-2-1-003 | AT must define the risk tolerance and target SLs for the organization. This is a critical input for the SI.
5 | Risk Assessment | 2025-12-12 | No | Dependent on schedule for completion after in workshops with SICE/CTEK and AT separately, are completed, and changes are "accepted" . Need Schedule, NCC - CBN VON-75 This is a change in Design/Architecture. It impacts the CSMP (IEC 62443 ZCR) CBN (will take into account VN-75 Actions to be taken. Currently listed as; PT-2 - NTP Time Source PT-9 - Quality of Service PT-14 - Security Verification - Full impact of the verification testing for this is however not yet clear. Depends on AT and how the test goes. SICE has no control over this PGL-4 - Backup Port Speed PGL-6 - Break Glass Accounts PGL-7 - Asset Register PGL-8 - Warning Banner PoGL-5 - Backup Verification | NCC | High Level Risk Assessment (Initial Risk Assessment) | Risk Assessment | RA-3-2-001 | High-Level Cyber Risk Assessment | IEC 62443-3-2 | High | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) | Asset Owner (AT) | SI (Link Alliance) - Executes Assessment ¦ Asset Owner (AT) - Approves ¦ Supplier (Honeywell) - Provides Info | SI (Link Alliance) | Review and Acceptance of Risk Assessment Report | Risk assessment methodology (AO-2-1-003) was followed; Initial zones identified; High-level risks documented. | Risk Assessment Report | ISO 27005 | Incomplete | Project Initiation | AO-2-1-003 | Initial risk assessment to define scope and boundaries. Feeds into system design.
6 | Risk Assessment | 2025-12-25 | No | Dependent on Asset inventory & Software configuration completed. This can be updated as asset registers are updated. Since final Asset inventory is due Dec 25, the Finacl CSMS (referencing asset registry, and therefore controls) will be after. | Link Alliance | Asset ; Hardware and Software Configuration Inventory/Register | Risk Assessment | RA-3-2-002 | Asset Inventory | IEC 62443-3-2 | High | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) | Asset Owner (AT) | SI (Link Alliance) - Compiles ¦ Supplier (Honeywell) - Provides Component List ¦ Asset Owner (AT) - Provides existing asset info | SI (Link Alliance) | Review and verification of inventory | Inventory is complete, accurate, and includes all required fields (IP, MAC, firmware, OS, location, zone). | Spreadsheet / CMDB | ISO 27001 A.8 | Incomplete | Project Initiation / Design | None | Critical input for the risk assessment. Must be maintained throughout the project.
7 | Risk Assessment | 2025-11-30 | No | Adjusting CBN based on VN-75, RACI with LA and AK and Asset Register and Software Register | NCC | Zone and Conduit Diagram | Risk Assessment | RA-3-2-003 | Zone and Conduit Definition | IEC 62443-3-2 | High | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) | Asset Owner (AT) | SI (Link Alliance) - Defines Zones ¦ Asset Owner (AT) - Approves ¦ Supplier (Honeywell) - Provides system architecture info | SI (Link Alliance) | Review and acceptance of Zone/Conduit diagrams and report | Zones group assets of same SL-T; Conduits identified; All data flows mapped; Aligns with AT's SL-T policy (AO-2-1-004). | Network Diagrams, Zone & Conduit Report | NIST SP 800-82 | Incomplete | Design Phase | RA-3-2-001, RA-3-2-002, AO-2-1-004 | This is the foundational architecture document for security.
8 | Risk Assessment | 2025-11-30 | No | Adjusting CBN based on VN-75, RACI with LA and AK and Asset Register and Software Register | NCC | Detailed Risk Assessment | Risk Assessment | RA-3-2-004 | Detailed Cyber Risk Assessment | IEC 62443-3-2 | High | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) | Asset Owner (AT) | SI (Link Alliance) - Executes Assessment ¦ Asset Owner (AT) - Approves ¦ Supplier (Honeywell) - Provides threat/vulnerability info | SI (Link Alliance) | Review and Acceptance of Detailed Risk Assessment Report | Threats, vulnerabilities, and consequences analyzed per-zone; SL-T confirmed for each zone; Risk register populated with mitigations. | Risk Assessment Report, Risk Register | ISO 27005 | Incomplete | Design Phase | RA-3-2-003 | Detailed assessment of the design defined in the Zone/Conduit report.
9 | Risk Assessment | 2025-11-30 | No | Adjusting CBN based on VN-75, RACI with LA and AK and Asset Register and Software Register. NCC - This is derived from the final Detailed Risk Assessment (modified from original CBN (to account for VN-75, RACI to AT captured in "Handover Plan", and MR. These will be the final FR and SR (Technical security requiremetns based on determined "Zone" level (1,2,3 or 4) | NCC | Technical Security Control Requirements | Risk Assessment | RA-3-2-005 | Cybersecurity Requirements Specification (CSRS) | IEC 62443-3-2 / 3-3 | High | SI (Link Alliance) | Asset Owner (AT) |  | Asset Owner (AT) | SI (Link Alliance) - Authors Specification ¦ Asset Owner (AT) - Approves | SI (Link Alliance) | Formal review and approval of CSRS document | CSRS includes all system-level requirements (from 3-3) mapped to SL-T; Non-technical requirements (from 2-4) included. All requirements are testable. | Requirements Specification Document | IEC 62443-3-3 | Incomplete | Design Phase | RA-3-2-004 | This document defines WHAT security controls must be built. It is the primary input to Design.
10 | Design | 2025-11-30 | Yes | NCC - to reference in Cyber Security Management Plan - Appendix (plus summary in main document) | NCC | High Level Security Design | Design | DES-3-3-001 | High-Level Security Design (HLD) | IEC 62443-3-3 | High | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) | Asset Owner (AT) | SI (Link Alliance) - Creates HLD ¦ Asset Owner (AT) - Approves ¦ Supplier (Honeywell) - Provides design input | SI (Link Alliance) | Review and approval of HLD package | HLD addresses all requirements in CSRS; Shows conceptual architecture, zone boundaries, and key security services. | Design Documents, Diagrams | SABSA, TOGAF | Incomplete | Design Phase | RA-3-2-005 | High-level design showing *how* the CSRS will be met.
11 | Design | 2025-11-21 | Yes | NCC - to reference in Cyber Security Management Plan - Appendix (plus summary in main document) | NCC | Detailed Security Desgin | Design | DES-3-3-002 | Detailed Security Design (DLD) - Network | IEC 62443-3-3 SR 3.1, 5.1, 5.2 | High | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) | Asset Owner (AT) | SI (Link Alliance) - Creates DLD ¦ Asset Owner (AT) - Approves ¦ Supplier (Honeywell) - Provides component configuration details | SI (Link Alliance) | Review and approval of Network DLD | DLD includes IP plan, VLANs, firewall rulesets (port/protocol/service), conduit definitions, remote access design. Traceable to HLD and CSRS. | Network Diagrams, Configuration Templates, Rulebase | NIST SP 800-41 | Incomplete | Design Phase | DES-3-3-001 | Detailed, build-ready design for all network security components.
12 | Design | 2025-11-21 | Yes | NCC - to reference in Cyber Security Management Plan - Appendix (plus summary in main document) | NCC | Detailed Security Design | Design | DES-3-3-003 | Detailed Security Design (DLD) - System | IEC 62443-3-3 SR 1.x, 2.x, 3.x, 4.x, 6.x, 7.x | High | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) | Asset Owner (AT) | SI (Link Alliance) - Creates DLD ¦ Asset Owner (AT) - Approves ¦ Supplier (Honeywell) - Provides component hardening/security guides | SI (Link Alliance) | Review and approval of System DLD | DLD includes hardening guides (per CIS), user/account matrix (RBAC), backup plan, AV/patching design, logging (SIEM) design. Traceable to HLD and CSRS. | Design Documents, Hardening Guides, Procedures | NIST SP 800-123, CIS Benchmarks | Incomplete | Design Phase | DES-3-3-001 | Detailed, build-ready design for all system-level (server, workstation, controller) security.
13 | Design | 2025-11-21 | Yes | Available via documents, Asset register and software/configuration register | NCC | Supplier Security Program Evidence | Design | DES-2-4-001 | Supplier Security Program Evidence | IEC 62443-2-4 | Medium | Supplier (Honeywell) | SI (Link Alliance) | Supplier (Honeywell) | Asset Owner (AT) | Supplier (Honeywell) - Provides Evidence ¦ SI (Link Alliance) - Assesses Evidence | Supplier (Honeywell) | Review of supplier documentation against IEC 62443-2-4 requirements | Supplier provides evidence of secure development (4-1 certs/docs), patch mgt, vulnerability handling, EOL policy. | Supplier Documentation, Certificates (e.g., 4-1, 4-2) | IEC 62443-4-1, 4-2 | Incomplete | Design Phase | RA-3-2-005 | Evidence from the Supplier (Honeywell) that they meet their security obligations as a vendor.
14 | Implementation | 2025-12-12 | No | NCC - to reference in Cyber Security Management Plan - Appendix (plus summary in main document). In appendix so will adjust based on indiivual outcome due to limitations | Link Alliance | System Build and Configuration Records | Implementation | IMPL-3-3-001 | System Build and Configuration Records | IEC 62443-3-3 | High | SI (Link Alliance) | SI (Link Alliance) | Supplier (Honeywell) | Asset Owner (AT) | SI (Link Alliance) - Builds and Configures System ¦ Supplier (Honeywell) - Provides secure configuration guides | SI (Link Alliance) | Verification during FAT/SAT; Handover of as-built docs | As-built system matches the approved DLDs (DES-3-3-002, DES-3-3-003). All deviations documented and approved. | As-Built Diagrams, Configuration Files, Build Sheets | N/A | Incomplete | Implementation Phase | DES-3-3-002, DES-3-3-003 | The actual, implemented system configuration.
15 | Implementation | 2025-12-12 | No | NCC - to reference in Cyber Security Management Plan - Appendix (plus summary in main document). In appendix so will adjust based on indiivual outcome due to limitations | Link Alliance | Firewall / Network Device Configurations | Implementation | IMPL-3-3-002 | Firewall / Network Device Configurations | IEC 62443-3-3 SR 5.1, 5.2 | High | SI (Link Alliance) | SI (Link Alliance) |  | Asset Owner (AT) | SI (Link Alliance) - Implements Configurations | SI (Link Alliance) | Verification during FAT/SAT; Handover of as-built configs | Firewall rulesets and network configs match the approved Network DLD (DES-3-3-002). | Configuration Files, As-Built Diagrams | N/A | Incomplete | Implementation Phase | DES-3-3-002 | As-built configuration files for all network security devices.
16 | Implementation | 2025-12-12 | No | NCC - to reference in Cyber Security Management Plan - Appendix (plus summary in main document). In appendix so will adjust based on indiivual outcome due to limitations | Link Alliance | Server and Workstation Hardening Records | Implementation | IMPL-3-3-003 | Server and Workstation Hardening Records | IEC 62443-3-3 SR 3.x, 4.x | High | SI (Link Alliance) | SI (Link Alliance) | Supplier (Honeywell) | Asset Owner (AT) | SI (Link Alliance) - Applies Hardening ¦ Supplier (Honeywell) - Provides guides | SI (Link Alliance) | Verification during FAT/SAT (e.g., vulnerability scan); Handover of build scripts/records | All servers, workstations, and devices are hardened per the System DLD (DES-3-3-003) and CIS benchmarks. | Hardening Checklists, Vulnerability Scan Reports, GPO Reports | CIS Benchmarks | Incomplete | Implementation Phase | DES-3-3-003 | Proof that systems were securely configured.
17 | Implementation | 2025-12-12 | No | NCC - to reference in Cyber Security Management Plan - Appendix (plus summary in main document). In appendix so will adjust based on indiivual outcome due to limitations | Link Alliance | User Account and Access Control Setup | Implementation | IMPL-3-3-004 | User Account and Access Control Setup | IEC 62443-3-3 SR 1.1, 1.2, 1.3 | High | SI (Link Alliance) | SI (Link Alliance) |  | Asset Owner (AT) | SI (Link Alliance) - Creates accounts per design | SI (Link Alliance) | Verification during SAT; Handover of initial account list | User accounts and access privileges (e.g., in Active Directory) match the approved System DLD (DES-3-3-003). | Account List, AD Group Configuration | N/A | Incomplete | Implementation Phase | DES-3-3-003 | List of all initial user accounts, groups, and permissions.
18 | Implementation | 2025-12-12 | No | NCC - to reference in Cyber Security Management Plan - Appendix (plus summary in main document). In appendix so will adjust based on indiivual outcome due to limitations | Link Alliance | Network Monitoring System (IDS/SIEM) Baseline | Implementation | IMPL-3-3-005 | Network Monitoring System (IDS/SIEM) Baseline | IEC 62443-3-3 SR 6.1, 6.2 | High | SI (Link Alliance) | SI (Link Alliance) | Supplier (Honeywell) | Asset Owner (AT) | SI (Link Alliance) - Implements and Baselines ¦ Supplier (Honeywell) - Provides component logs/MIBs | SI (Link Alliance) | Verification during SAT; Handover of SIEM configuration | SIEM/IDS is configured, collecting logs from all in-scope assets, and tuned to establish a 'normal' baseline. Use cases are active. | SIEM Configuration File, Baseline Report, Use Case Docs | N/A | Incomplete | Implementation Phase | DES-3-3-003 | Configuration of the security monitoring tools.
19 | Implementation | 2025-12-12 | No | NCC - to reference in Cyber Security Management Plan - Appendix (plus summary in main document). In appendix so will adjust based on indiivual outcome due to limitations | Link Alliance | Backup and Recovery System Configuration | Implementation | IMPL-3-3-006 | Backup and Recovery System Configuration | IEC 62443-3-3 SR 7.1, 7.2 | High | SI (Link Alliance) | SI (Link Alliance) |  | Asset Owner (AT) | SI (Link Alliance) - Configures Backup System | SI (Link Alliance) | Verification during SAT (test restore); Handover of backup job configs | Backup system is configured per System DLD (DES-3-3-003) and a successful test restore of each system type is completed. | Backup Job Logs, Test Restore Report | NIST SP 800-34 | Incomplete | Implementation Phase | DES-3-3-003 | Configuration of the backup solution.
20 | Implementation | 2025-12-12 | No | NCC - to reference in Cyber Security Management Plan - Appendix (plus summary in main document). In appendix so will adjust based on indiivual outcome due to limitations | Link Alliance | Configuration Baselines | Implementation | IMPL-3-3-007 | Configuration Baselines | IEC 62443-3-3 SR 7.3 | High | SI (Link Alliance) | SI (Link Alliance) |  | Asset Owner (AT) | SI (Link Alliance) - Creates baselines of all configurations | SI (Link Alliance) | Review and acceptance of baseline package | Baselines (e.g., config files, hashes, software versions) are captured for all assets post-SAT, prior to Go-Live. | Configuration Files, Baseline Checksum Report (SHA-256) | N/A | Incomplete | Implementation Phase | IMPL-3-3-001, IMPL-3-3-002, IMPL-3-3-003 | A 'golden image' or 'golden config' of the entire system at handover.
21 | Implementation | 2025-12-12 | No | NCC - to reference in Cyber Security Management Plan - Appendix (plus summary in main document). In appendix so will adjust based on indiivual outcome due to limitations | Link Alliance | Physical Security Controls (As-Built) | Implementation | IMPL-3-3-008 | Physical Security Controls (As-Built) | IEC 62443-3-3 SR 2.1, 2.2 | Medium | SI (Link Alliance) | SI (Link Alliance) |  | Asset Owner (AT) | SI (Link Alliance) - Installs and documents physical controls | SI (Link Alliance) | Site walkdown and inspection | Physical controls (locks, access control, cabinet locations) are implemented as per the design. | As-Built Drawings, Site Photos | ISO 27001 A.11 | Incomplete | Implementation Phase | DES-3-3-001 | Documentation of the as-built physical security.
22 | Implementation | 2025-12-12 | No | NCC - to reference in Cyber Security Management Plan - Appendix (plus summary in main document). In appendix so will adjust based on indiivual outcome due to limitations | Link Alliance | Patch Management and AV Procedures | Implementation | IMPL-3-3-009 | Patch Management and AV Procedures | IEC 62443-3-3 SR 3.2, 3.4 | High | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) | Operator (Maintenance SP) | SI (Link Alliance) - Authors procedures ¦ Supplier (Honeywell) - Provides patch/AV info ¦ Asset Owner (AT) - Approves | SI (Link Alliance) | Review and acceptance of procedures by Operator | Procedures are clear, testable, and specific to the IACS. Cover testing, approval, and deployment. Aligns with CSMS-012. | Procedure Documents | N/A | Incomplete | Implementation Phase | DES-3-3-003, CSMS-012 | The 'how-to' guide for the Operator to manage patches and AV.
23 | Testing |  | No |  | Link Alliance |  | Testing | TEST-3-3-001 | Factory Acceptance Test (FAT) - Security | IEC 62443-3-3 | High | SI (Link Alliance) | SI (Link Alliance) | Supplier (Honeywell) | Asset Owner (AT) | SI (Link Alliance) - Executes Tests ¦ Supplier (Honeywell) - Supports ¦ Asset Owner (AT) - Witnesses/Approves | N/A - Internal SI milestone | Asset Owner witness and approval of FAT Report | All security controls are tested per test plan; results documented; deviations recorded. Test plan is traceable to CSRS (RA-3-2-005). | FAT Security Test Plan, FAT Security Test Report | N/A | Incomplete | Testing Phase | IMPL-3-3-001, RA-3-2-005 | Testing of the system in the SI's factory/lab.
24 | Testing |  | No |  | Link Alliance |  | Testing | TEST-3-3-002 | Site Acceptance Test (SAT) - Security | IEC 62443-3-3 | High | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) | Operator (Maintenance SP) | SI (Link Alliance) - Executes Tests ¦ Asset Owner (AT) - Witnesses/Approves ¦ Operator (Maintenance SP) - Witnesses | Asset Owner (AT) | Formal sign-off of SAT Report by Asset Owner | All security controls tested on-site; system performs as per CSRS; baseline captured (IMPL-3-3-007). Test plan is traceable to CSRS. | SAT Security Test Plan, SAT Security Test Report | N/A | Incomplete | Testing Phase | TEST-3-3-001, RA-3-2-005 | Final testing of the system on-site at CRL.
25 | Testing | 2025-01-15 | No | NCC - advise that "testing" (sampling of key configurations at a station occur in Dec/Jan, then referenced in CSMP | Link Alliance | Site Acceptance Test | Testing | TEST-3-3-003 | Vulnerability Scan Report (Pre-Handover) | IEC 62443-3-3 | High | SI (Link Alliance) | Asset Owner (AT) |  | Operator (Maintenance SP) | SI (Link Alliance) - Conducts Scan ¦ Asset Owner (AT) - Approves results | SI (Link Alliance) | Review and acceptance of scan report and remediation plan | Scan completed on final as-built system; All critical/high vulnerabilities remediated or risk-accepted by AT. | Vulnerability Scan Report, Remediation Plan | N/A | Incomplete | Testing Phase | TEST-3-3-002 | Final vulnerability scan before the system is handed over.
26 | Testing | 2025-01-15 | No | NCC - advise that "testing" (sampling of key configurations at a station occur in Dec/Jan, then referenced in CSMP | Link Alliance | Vulnerability Scan Report | Testing | TEST-3-3-004 | Penetration Test Report (if required) | IEC 62443-3-3 | Medium | SI (Link Alliance) | Asset Owner (AT) |  | Operator (Maintenance SP) | Third-Party Tester - Executes ¦ SI (Link Alliance) - Coordinates ¦ Asset Owner (AT) - Accepts | Third-Party Tester / SI | Review and acceptance of test report and remediation plan | Penetration test (if scoped by AO) completed; All critical/high findings remediated or risk-accepted by AT. | Penetration Test Report, Remediation Plan | N/A | Incomplete | Testing Phase | TEST-3-3-002 | Optional, more in-depth security test by a third party.
27 | Operations | 2025-12-12 | No | NCC - to compose Handover document to AT, as Responsible Party | NCC | Hand Over Plan | Handover | HO-2-1-001 | Incident Response Plan (System-Specific) | IEC 62443-2-1 SR 2.9 | High | SI (Link Alliance) | Asset Owner (AT) |  | Operator (Maintenance SP) | SI (Link Alliance) - Authors plan ¦ Asset Owner (AT) - Approves ¦ Operator (Maintenance SP) - Accepts | SI (Link Alliance) | Review, acceptance, and tabletop exercise of the plan | Plan contains specific playbooks for IACS (e.g., malware, unauthorized access); Contact lists are accurate. Aligns with CSMS-005. | Procedure Document | NIST SP 800-61 | Incomplete | Handover Phase | DES-3-3-003, IMPL-3-3-005, CSMS-005 | The 'how-to' guide for the Operator to handle a security incident.
28 | Operations | 2025-12-12 | No | NCC - to compose Handover document to AT, as Responsible Party | NCC | Hand Over Plan | Handover | HO-2-1-002 | Disaster Recovery Plan (System-Specific) | IEC 62443-2-1 SR 2.10 | High | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) | Operator (Maintenance SP) | SI (Link Alliance) - Authors plan ¦ Supplier (Honeywell) - Provides restore info ¦ Asset Owner (AT) - Approves | SI (Link Alliance) | Review, acceptance, and DR test (post-handover) | Plan details full system-from-bare-metal recovery; RTO/RPO defined; Aligns with IMPL-3-3-006. Aligns with CSMS-006. | Procedure Document | NIST SP 800-34 | Incomplete | Handover Phase | IMPL-3-3-006, CSMS-006 | The 'how-to' guide for the Operator to recover from a total system failure.
29 | Operations | 2025-12-12 | No | NCC - to compose Handover document to AT, as Responsible Party | NCC | Hand Over Plan | Handover | HO-2-1-003 | Security Training Materials (for Operator) | IEC 62443-2-1 SR 2.7 | Medium | SI (Link Alliance) | Asset Owner (AT) |  | Operator (Maintenance SP) | SI (Link Alliance) - Creates and delivers training | SI (Link Alliance) | Attendance at training session; Acceptance of training materials | Training covers day-to-day security operations (patching, backups, incident response, etc.) for the specific IACS. Aligns with CSMS-007. | Training Slides, Manuals, Attendance Register | N/A | Incomplete | Handover Phase | All operational procedures (patch, backup, IR, DR), CSMS-007 | Training session and materials for the end-users and administrators.
30 | Operations | 2025-12-12 | No | NCC - to compose Handover document to AT, as Responsible Party | NCC | Hand Over Plan | Handover | HO-FINAL-001 | Final Handover Package / Security Case | N/A | High | SI (Link Alliance) | Asset Owner (AT) |  | Operator (Maintenance SP) | SI (Link Alliance) - Compiles all project artifacts | SI (Link Alliance) | Formal acceptance of the complete artifact package | This is the final administrative compilation and handover of all project artifacts. The *argument* for security acceptance is contained in the COMP-SEC-CASE artifacts. | Document / Data Package | N/A | Incomplete | Handover Phase | All other artifacts, COMP-SEC-CASE-009 | The complete, zipped-up folder of all project documentation, submitted for final acceptance.
31 | Operations | 2025-05-01 | No |  | AT |  | Maintenance | MAINT-2-4-001 | Security Maintenance Agreement (Supplier) | IEC 62443-2-4 | High | Asset Owner (AT) | Asset Owner (AT) | Supplier (Honeywell) | Operator (Maintenance SP) | Asset Owner (AT) - Procures Agreement ¦ Supplier (Honeywell) - Provides | N/A - Contractual | N/A - Contractual | Contract with Supplier (Honeywell) is in place, guaranteeing patch/vulnerability notifications and support. | Contract / Agreement | N/A | Incomplete | Post-PC Ongoing | None | The formal support contract with the main product supplier (Honeywell).
32 | Operations | 2025-05-01 | No |  | AT |  | Maintenance | MAINT-2-4-002 | Security Maintenance Agreement (Integrator/Operator) | IEC 62443-2-4 | High | Asset Owner (AT) | Asset Owner (AT) | Operator (Maintenance SP) | Operator (Maintenance SP) | Asset Owner (AT) - Procures Agreement ¦ Operator (Maintenance SP) - Provides | N/A - Contractual | N/A - Contractual | Contract with Operator (Maintenance SP) is in place, defining all security responsibilities (patching, monitoring, etc.). | Contract / Agreement | N/A | Incomplete | Post-PC Ongoing | None | The formal support contract with the maintenance provider (Operator).
33 | Operations | 2025-05-01 | No |  | AT |  | Maintenance | MAINT-2-1-003 | Change Management Records | IEC 62443-2-1 SR 2.5 | High | Operator (Maintenance SP) | Asset Owner (AT) | SI (Link Alliance) |  | Operator (Maintenance SP) - Implements Changes ¦ Asset Owner (AT) - Approves Changes | N/A - Ongoing operational record | Periodic audit of change records | All changes to the IACS (patches, config changes, etc.) follow the formal, approved change management process (CSMS-009). | Change Management Records | ITIL | Ongoing | Post-PC Ongoing | IMPL-3-3-007 (baselines), CSMS-009 | Per RACI: Maintenance SP=R implements changes, AO=A must approve. Uses baselines Link Alliance established.
34 | Operations | 2025-05-01 | No |  | AT |  | Maintenance | MAINT-2-4-004 | Security Measures Updates | IEC 62443-2-4 | Medium | Operator (Maintenance SP) | Asset Owner (AT) | Supplier (Honeywell) |  | Operator (Maintenance SP) - Updates Security Measures ¦ Asset Owner (AT) - Approves ¦ Supplier (Honeywell) - Provides Updates | N/A - Ongoing operational record | N/A - Ongoing | Operator (Maintenance SP) updates organizational and technical security measures as needed per procedures. | Security Update Records | N/A | Ongoing | Post-PC Ongoing | IMPL-3-3-009 (patch procedures) | Per RACI: Maintenance SP=R updates, AO=A approves, PS=C provides updates. Ongoing per procedures Link Alliance developed.
35 | Operations | 2025-05-01 | No |  | AT |  | Maintenance | MAINT-PATCH-001 | Patch Management Execution and Tracking | IEC 62443-3-3 SR 3.2, 2-3 | High | Operator (Maintenance SP) | Asset Owner (AT) | Supplier (Honeywell) |  | Operator (Maintenance SP) - Executes Patching ¦ Asset Owner (AT) - Approves ¦ Supplier (Honeywell) - Provides Patches | N/A - Ongoing patch tracking | Periodic audit of patch records | Operator (Maintenance SP) tracks all patches: tested, approved, deployed, rolled back per patch management procedures (IMPL-3-3-009). | Patch Management Records + Dashboard | ISO 27002 | Ongoing | Post-PC Ongoing | IMPL-3-3-009 (procedures) | Operator (Maintenance SP) executes patch management procedures Link Alliance developed. Honeywell provides patches per IEC 62443-2-3.
36 | Operations | 2025-05-01 | No |  | AT |  | OPS - Ongoing Operations | OPS-001 | Security Monitoring Logs | IEC 62443-3-3 SR 3.3 | High | Operator (Maintenance SP) | Asset Owner (AT) |  |  | Operator generates, collects, and reviews security monitoring logs from IACS assets. | N/A - Operational Artifact | Ongoing review by security team; Periodic audit | Logs are collected from all in-scope devices, retained for retention period, and reviewed per incident response plan (HO-2-1-001). | Log Files (SIEM) | ISO 27001 A.12.4 | Ongoing | Ongoing | IMPL-3-3-005 (Network Monitoring) | Ongoing operational activity executed by the Operator.
37 | Operations | 2025-05-01 | No |  | AT |  | OPS - Ongoing Operations | OPS-002 | Firewall Rule Review Records | IEC 62443-3-3 SR 3.1 | High | Operator (Maintenance SP) | Asset Owner (AT) |  |  | Operator conducts periodic reviews of all firewall and ACL rules. | N/A - Operational Artifact | Periodic review and approval of rule sets | Review conducted quarterly; All rules are documented with business justification; 'Any/Any' rules are prohibited. | Review Report / Change Records | NIST SP 800-41 | Ongoing | Ongoing | DES-3-3-002 (Network Segmentation) | Ongoing operational activity executed by the Operator.
38 | Operations | 2025-12-12 | No | NCC - to include only if Incident occurs prior to CR | NCC | Cyber Security Management Plan | OPS - Ongoing Operations | OPS-003 | Security Incident Records | IEC 62443-2-1 SR 2.9 | High | Operator (Maintenance SP) | Asset Owner (AT) |  |  | Operator documents and manages all security incidents per the IRP. | N/A - Operational Artifact | Post-incident review | All incidents are documented, tracked, and closed per the Incident Response Plan (HO-2-1-001). | Incident Tickets / Report | ISO 27035 | Ongoing | Ongoing | HO-2-1-001 (Incident Response Plan) | Ongoing operational activity executed by the Operator.
39 | Operations | 2025-05-01 | No |  | AT |  | OPS - Ongoing Operations | OPS-006 | Security Training Records | IEC 62443-2-1 SR 2.7 | Medium | Operator (Maintenance SP) | Asset Owner (AT) |  |  | Operator (AT) ensures all staff (internal and contractor) receive appropriate annual security awareness training. | N/A - Operational Artifact | Periodic audit of training records | All IACS staff and privileged users have completed annual security training per CSMS-007. | Training Attendance Register | ISO 27001 | Ongoing | Ongoing | HO-2-1-003 (Training Materials), CSMS-007 | Ongoing management of personnel security awareness.
40 | Operations | 2025-05-01 | No |  | AT |  | OPS - Ongoing Operations | OPS-007 | Vendor Security Assessment Results | IEC 62443-2-1 SR 2.4 | Medium | Operator (Maintenance SP) | Asset Owner (AT) |  |  | Operator (AT) conducts periodic security assessments of critical vendors (e.g., Maintenance SP, Suppliers). | N/A - Operational Artifact | Review of assessment results | Periodic assessments are conducted per CSMS-020; Findings are tracked to remediation. | Assessment Report | ISO 27036 | Ongoing | Ongoing | MAINT-2-4-001, MAINT-2-4-002, CSMS-020 | Ongoing supply chain risk management by the Asset Owner/Operator.
41 | Operations | 2025-05-01 | No |  | AT |  | OPS - Ongoing Operations | OPS-008 | Security Metrics Dashboard | IEC 62443-2-1 SR 2.11 | Medium | Operator (Maintenance SP) | Asset Owner (AT) |  |  | Operator (AT) maintains and reports on security metrics (e.g., patch status, incidents, config changes). | N/A - Operational Artifact | Monthly/Quarterly Security Review | Dashboard is maintained and presented to Asset Owner management per CSMS-022. | Dashboard / Report | ISO 27004 | Ongoing | Ongoing | All other artifacts, CSMS-022 | Provides management visibility into the health of the CSMS.
42 | Compliance | 2025-05-01 | No |  | AT |  | COMP-REG - Compliance - OPTIONAL | COMP-REG-002 | Rail Safety National Law (RSNL) Cybersecurity Integration | RSNL (NZ) | High | Asset Owner (AT) | Asset Owner (AT) | SI (Link Alliance) | Operator (Maintenance SP) | Asset Owner (AT) - Ensures integration into Safety Management System (SMS) ¦ SI - Provides cyber inputs | SI (Link Alliance) | Review of SMS cybersecurity-related clauses and risk assessments. | Cybersecurity risks (from RA-3-2-004) are explicitly identified and addressed within the formal Safety Management System (SMS) as required by RSNL. | SMS Documentation (updated), Risk Register | RSNL | Incomplete | Handover Phase | RA-3-2-004 (Detailed Risk Assessment) | Crucial artifact linking the IEC 62443 (cybersecurity) and RSNL (safety) worlds. This demonstrates that cyber risks are treated as potential safety risks.
43 | Compliance | 2025-05-01 | No |  | AT |  | COMP-REG - Compliance - OPTIONAL | COMP-REG-003 | NZISM Compliance Package | NZISM | High | SI (Link Alliance) | Asset Owner (AT) | Operator (Maintenance SP) |  | SI (Link Alliance) - Compiles compliance package ¦ Asset Owner (AT) - Accepts package | SI (Link Alliance) | Review of System Security Plan (SSP) and compliance matrix against NZISM controls. | A complete compliance package (e.g., System Security Plan, risk register, control matrix) is provided, mapping all applicable NZISM controls to project artifacts (e.g., DLDs, test reports). | System Security Plan (SSP), Compliance Matrix, Risk Assessment Report | NZISM, ISO 27001 | Incomplete | Handover Phase | All DES, IMPL, and TEST artifacts, COMP-SEC-CASE-009 | This is a key handover artifact for NZ government projects. It bundles many other artifacts into a format for formal security accreditation and acceptance.
44 | Program Management | 2025-11-30 | No |  | NCC |  | CSMS - Program Management | CSMS-001 | Cybersecurity Management System (CSMS) Plan | IEC 62443-2-1 | High | SI (Link Alliance) | Asset Owner (AT) |  | Operator (Maintenance SP) | SI (Link Alliance) - Establishes system-specific CSMS ¦ Asset Owner (AT) - Approves and adopts | SI (Link Alliance) | Review and acceptance of CSMS plan by Asset Owner. | Plan is delivered by SI, is specific to the CRL system, and aligns with AT's organizational policies (AO-2-1-001). It must be suitable for AT to adopt for ongoing operations. | Program Documentation | ISO 27001 | Incomplete | Before Project Starts | AO-2-1-001 | This is the *system-specific* CSMS framework delivered by the SI as a project artifact, which is then adopted by the AO who is accountable for the *organizational* CSMS.
45 | Program Management | 2025-11-30 | No |  | NCC |  | CSMS - Program Management | CSMS-002 | CSMS Security Policy | IEC 62443-2-1 SR 1.1 | High | SI (Link Alliance) | Asset Owner (AT) |  |  | SI (Link Alliance) - Drafts system-specific policy ¦ Asset Owner (AT) - Approves and issues | SI (Link Alliance) | Review and approval of system-specific policies by AT. | Policies are specific to the CRL IACS, align with AT's high-level policy (AO-2-1-002), and are actionable. | Policy Documents | ISO 27001 | Incomplete | Before Project Starts | CSMS-001, AO-2-1-002 | This is the *system-specific* policy set delivered by the SI, which implements the AT's *organizational* policy.
46 | Program Management | 2025-11-30 | Yes | NCC - Cyber Security Management Plan - Appendix (plus summary reference in main document) | NCC | NCC - Cyber Security Management Plan - Appendix (plus summary reference in main document) | CSMS - Program Management | CSMS-003 | Organizational Structure and Responsibilities | IEC 62443-2-1 SR 1.2 | High | SI (Link Alliance) | Asset Owner (AT) |  | Operator (Maintenance SP) | SI (Link Alliance) - Defines project & ops roles ¦ Asset Owner (AT) - Approves | SI (Link Alliance) | Review and approval of RACI matrix by AT. | Roles, responsibilities, and authorities for IACS cybersecurity *for the CRL system* are defined (e.g., SI, Operator, AT roles). | RACI Matrix, Org Chart | ISO 27001 A.7 | Incomplete | Before Project Starts | CSMS-001 | This defines the 'who' for the CRL system, which is then adopted into the AT's organizational structure.
47 | Program Management | 2025-11-30 | No | NCC - to compose Handover document to AT, as Responsible Party | NCC | NCC - Cyber Security Management Plan | CSMS - Program Management | CSMS-004 | Risk Management Process | IEC 62443-2-1 SR 2.3 | High | SI (Link Alliance) | Asset Owner (AT) |  |  | SI (Link Alliance) - Executes process ¦ Asset Owner (AT) - Approves methodology | SI (Link Alliance) | Review and approval of risk management outputs (RA-3-2-004). | The *execution* of the risk management process defined by AT (AO-2-1-003). This artifact represents the *implementation* of that process. | Risk Assessment Report | ISO 27005 | Incomplete | Project Initiation | CSMS-001, AO-2-1-003 | This is the *execution* of the risk process by the SI, based on the *methodology* defined by AT.
48 | Program Management | 2025-12-12 | No | NCC - to compose Handover document to AT, as Responsible Party | AT | Incident Response Plan (Organizational) | CSMS - Program Management | CSMS-005 | Incident Response Plan (Organizational) | IEC 62443-2-1 SR 2.9 | High | Asset Owner (AT) | Asset Owner (AT) |  | Operator (Maintenance SP) | Asset Owner (AT) - Establishes | Not Handed Over - AT Internal Program | N/A - AT internal governance | The high-level *organizational* plan for managing IACS incidents. | Procedure Document | NIST SP 800-61 | Incomplete | Before Project Starts | CSMS-001 | This is the *organizational* plan. HO-2-1-001 is the *system-specific* plan for CRL delivered by the SI, which must align with this.
49 | Program Management | 2025-12-12 | No | NCC - to compose Handover document to AT, as Responsible Party | AT | Business Continuity / Disaster Recovery Plan (Organizational) | CSMS - Program Management | CSMS-006 | Business Continuity / Disaster Recovery Plan (Organizational) | IEC 62443-2-1 SR 2.10 | High | Asset Owner (AT) | Asset Owner (AT) |  | Operator (Maintenance SP) | Asset Owner (AT) - Establishes | Not Handed Over - AT Internal Program | N/A - AT internal governance | The high-level *organizational* plan for BCP/DR of IACS. | Procedure Document | NIST SP 800-34 | Incomplete | Before Project Starts | CSMS-001 | This is the *organizational* plan. HO-2-1-002 is the *system-specific* plan for CRL delivered by the SI, which must align with this.
50 | Program Management | 2025-12-12 | No | NCC - to compose Handover document to AT, as Responsible Party | AT | Security Awareness and Training Program | CSMS - Program Management | CSMS-007 | Security Awareness and Training Program | IEC 62443-2-1 SR 2.7 | Medium | Asset Owner (AT) | Asset Owner (AT) |  |  | Asset Owner (AT) - Establishes | Not Handed Over - AT Internal Program | N/A - AT internal governance | Program for ongoing security awareness and training for all IACS personnel is established. | Program Documentation | ISO 27001 A.7.2.2 | Incomplete | Before Project Starts | CSMS-001 | This is the *organizational* program. HO-2-1-003 is the *initial training delivery* for the CRL system, which must align with this.
51 | Program Management | 2025-12-12 | No | NCC - to compose Handover document to AT, as Responsible Party | AT | Personnel Security Procedure | CSMS - Program Management | CSMS-008 | Personnel Security Procedure | IEC 62443-2-1 SR 2.8 | Medium | Asset Owner (AT) | Asset Owner (AT) |  |  | Asset Owner (AT) - Establishes | Not Handed Over - AT Internal Program | N/A - AT internal governance | Procedures for background checks, onboarding, and offboarding for IACS personnel. | Procedure Document | ISO 27001 A.7 | Incomplete | Before Project Starts | CSMS-001 | Defines AT's internal HR security processes for IACS.
52 | Program Management | 2025-12-12 | No | NCC - to compose Handover document to AT, as Responsible Party | AT | Change Management (MOC) Process | CSMS - Program Management | CSMS-009 | Change Management (MOC) Process | IEC 62443-2-1 SR 2.5 | High | Asset Owner (AT) | Asset Owner (AT) |  |  | Asset Owner (AT) - Establishes | Not Handed Over - AT Internal Program | N/A - AT internal governance | The *organizational* process for Management of Change (MOC) for IACS. | Procedure Document | ITIL | Incomplete | Before Project Starts | CSMS-001 | This is the *organizational* process. MAINT-2-1-003 are the *records* of this process in action.
53 | Program Management | 2025-12-12 | No | NCC - to compose Handover document to AT, as Responsible Party | AT | Configuration Management Process | CSMS - Program Management | CSMS-010 | Configuration Management Process | IEC 62443-2-1 SR 2.5 | High | Asset Owner (AT) | Asset Owner (AT) |  |  | Asset Owner (AT) - Establishes | Not Handed Over - AT Internal Program | N/A - AT internal governance | The *organizational* process for configuration management. | Procedure Document | ITIL | Incomplete | Before Project Starts | CSMS-001 | This is the *organizational* process. IMPL-3-3-007 are the *initial baselines* for the CRL system.
54 | Program Management | 2025-12-12 | No | NCC - to compose Handover document to AT, as Responsible Party | AT | Asset Management Procedure | CSMS - Program Management | CSMS-011 | Asset Management Procedure | IEC 62443-2-1 SR 2.1 | Medium | Asset Owner (AT) | Asset Owner (AT) |  |  | Asset Owner (AT) - Establishes | Not Handed Over - AT Internal Program | N/A - AT internal governance | The *organizational* process for identifying and managing IACS assets. | Procedure Document | ISO 27001 A.8 | Incomplete | Before Project Starts | CSMS-001 | This is the *organizational* process. RA-3-2-002 is the *initial inventory* for the CRL system.
55 | Program Management | 2025-12-12 | No | NCC - to compose Handover document to AT, as Responsible Party | AT | Patch Management Plan (Organizational) | CSMS - Program Management | CSMS-012 | Patch Management Plan (Organizational) | IEC 62443-2-1 SR 2.12 | High | Asset Owner (AT) | Asset Owner (AT) |  |  | Asset Owner (AT) - Establishes | Not Handed Over - AT Internal Program | N/A - AT internal governance | The *organizational* plan and process for patch management. | Procedure Document | ISO 27002 | Incomplete | Before Project Starts | CSMS-001 | This is the *organizational* plan. IMPL-3-3-009 is the *system-specific procedure* delivered by the SI, which must align with this.
56 | Program Management | 2025-12-12 | No | NCC - to compose Handover document to AT, as Responsible Party | AT | Anti-Virus / Malware Protection Plan | CSMS - Program Management | CSMS-013 | Anti-Virus / Malware Protection Plan | IEC 62443-2-1 SR 2.12 | High | Asset Owner (AT) | Asset Owner (AT) |  |  | Asset Owner (AT) - Establishes | Not Handed Over - AT Internal Program | N/A - AT internal governance | The *organizational* plan for malware protection. | Procedure Document | N/A | Incomplete | Before Project Starts | CSMS-001 | This is the *organizational* plan. IMPL-3-3-009 is the *system-specific procedure* delivered by the SI, which must align with this.
57 | Program Management | 2025-12-12 | No | NCC - to compose Handover document to AT, as Responsible Party | AT | Backup and Recovery Procedure | CSMS - Program Management | CSMS-014 | Backup and Recovery Procedure | IEC 62443-2-1 SR 2.10 | High | Asset Owner (AT) | Asset Owner (AT) |  |  | Asset Owner (AT) - Establishes | Not Handed Over - AT Internal Program | N/A - AT internal governance | The *organizational* procedure for IACS backup and recovery. | Procedure Document | NIST SP 800-34 | Incomplete | Before Project Starts | CSMS-001 | This is the *organizational* procedure. HO-2-1-002 is the *system-specific plan* for CRL, which must align with this.
58 | Program Management | 2025-12-12 | No | NCC - to compose Handover document to AT, as Responsible Party | AT | Network Segmentation and Access Control Policy | CSMS - Program Management | CSMS-015 | Network Segmentation and Access Control Policy | IEC 62443-2-1 SR 2.2 | High | Asset Owner (AT) | Asset Owner (AT) |  |  | Asset Owner (AT) - Establishes | Not Handed Over - AT Internal Program | N/A - AT internal governance | The *organizational* policy for how IACS networks should be segmented. | Policy Document | NIST SP 800-82 | Incomplete | Before Project Starts | CSMS-001 | This is the *organizational* policy. RA-3-2-003 is the *system-specific design* for CRL, which must align with this.
59 | Program Management | 2025-12-12 | No | NCC - to compose Handover document to AT, as Responsible Party | AT | Identity and Access Management (IAM) Policy | CSMS - Program Management | CSMS-016 | Identity and Access Management (IAM) Policy | IEC 62443-2-1 SR 2.1 | High | Asset Owner (AT) | Asset Owner (AT) |  |  | Asset Owner (AT) - Establishes | Not Handed Over - AT Internal Program | N/A - AT internal governance | The *organizational* policy for IACS user accounts, passwords, and access control. | Policy Document | N/A | Incomplete | Before Project Starts | CSMS-001 | This is the *organizational* policy. DES-3-3-003 (DLD-System) defines the *system-specific* implementation.
60 | Program Management | 2025-12-12 | No | NCC - to compose Handover document to AT, as Responsible Party | AT | Physical and Environmental Security Policy | CSMS - Program Management | CSMS-017 | Physical and Environmental Security Policy | IEC 62443-2-1 SR 2.6 | Medium | Asset Owner (AT) | Asset Owner (AT) |  |  | Asset Owner (AT) - Establishes | Not Handed Over - AT Internal Program | N/A - AT internal governance | The *organizational* policy for securing IACS assets physically. | Policy Document | ISO 27001 A.11 | Incomplete | Before Project Starts | CSMS-001 | This is the *organizational* policy. IMPL-3-3-008 is the *as-built record* for CRL.
61 | Program Management | 2025-12-12 | No | NCC - to compose Handover document to AT, as Responsible Party | AT | Remote Access Policy | CSMS - Program Management | CSMS-018 | Remote Access Policy | IEC 62443-2-1 SR 2.1 | High | Asset Owner (AT) | Asset Owner (AT) |  |  | Asset Owner (AT) - Establishes | Not Handed Over - AT Internal Program | N/A - AT internal governance | The *organizational* policy defining requirements for remote access to IACS. | Policy Document | NIST SP 800-41 | Incomplete | Before Project Starts | CSMS-001 | This is the *organizational* policy. DES-3-3-002 (DLD-Network) defines the *system-specific* implementation.
62 | Program Management | 2025-12-12 | No | NCC - to compose Handover document to AT, as Responsible Party | AT | System Monitoring and Logging Policy | CSMS - Program Management | CSMS-019 | System Monitoring and Logging Policy | IEC 62443-2-1 SR 2.12 | High | Asset Owner (AT) | Asset Owner (AT) |  |  | Asset Owner (AT) - Establishes | Not Handed Over - AT Internal Program | N/A - AT internal governance | The *organizational* policy defining what must be logged and monitored. | Policy Document | ISO 27001 A.12 | Incomplete | Before Project Starts | CSMS-001 | This is the *organizational* policy. DES-3-3-003 (DLD-System) defines the *system-specific* implementation.
63 | Program Management | 2025-12-12 | No | NCC - to compose Handover document to AT, as Responsible Party | AT | Vendor and Supplier Management Procedure | CSMS - Program Management | CSMS-020 | Vendor and Supplier Management Procedure | IEC 62443-2-1 SR 2.4 | Medium | Asset Owner (AT) | Asset Owner (AT) |  |  | Asset Owner (AT) - Establishes | Not Handed Over - AT Internal Program | N/A - AT internal governance | The *organizational* procedure for assessing and managing supplier/vendor risk. | Procedure Document | ISO 27036 | Incomplete | Before Project Starts | CSMS-001 | This is the *organizational* procedure. DES-2-4-001 is the *execution* of this procedure for the CRL project.
64 | Program Management | 2025-12-12 | No | NCC - to compose Handover document to AT, as Responsible Party | AT | CSMS Audit and Review Plan | CSMS - Program Management | CSMS-021 | CSMS Audit and Review Plan | IEC 62443-2-1 SR 2.11 | Medium | Asset Owner (AT) | Asset Owner (AT) |  |  | Asset Owner (AT) - Establishes | Not Handed Over - AT Internal Program | N/A - AT internal governance | The *organizational* plan for auditing and reviewing the CSMS. | Procedure Document | ISO 27001 A.18 | Incomplete | Before Project Starts | CSMS-001 | This is the *organizational* plan. OPS-008 (Metrics) is an *input* to this process.
65 | Program Management | 2025-12-12 | No | NCC - to compose Handover document to AT, as Responsible Party | AT | CSMS Metrics and Reporting Procedure | CSMS - Program Management | CSMS-022 | CSMS Metrics and Reporting Procedure | IEC 62443-2-1 SR 2.11 | Medium | Asset Owner (AT) | Asset Owner (AT) |  |  | Asset Owner (AT) - Establishes | Not Handed Over - AT Internal Program | N/A - AT internal governance | The *organizational* procedure defining what metrics to collect and how to report them. | Procedure Document | ISO 27004 | Incomplete | Before Project Starts | CSMS-001 | This is the *organizational* procedure. OPS-008 is the *output* of this procedure.
66 | Program Management | 2025-12-12 | No | NCC - to compose Handover document to AT, as Responsible Party | AT | System Decommissioning Procedure | CSMS - Program Management | CSMS-023 | System Decommissioning Procedure | IEC 62443-2-1 | Medium | Asset Owner (AT) | Asset Owner (AT) |  |  | Asset Owner (AT) - Establishes | Not Handed Over - AT Internal Program | N/A - AT internal governance | The *organizational* procedure for securely decommissioning IACS assets. | Procedure Document | NIST SP 800-88 | Incomplete | Before Project Starts | CSMS-001 | Defines AT's process for end-of-life.
67 | Program Management | 2025-12-12 | No | NCC - to compose Handover document to AT, as Responsible Party | AT | Regulatory Compliance Procedure | CSMS - Program Management | CSMS-024 | Regulatory Compliance Procedure | IEC 62443-2-1 | High | Asset Owner (AT) | Asset Owner (AT) |  |  | Asset Owner (AT) - Establishes | Not Handed Over - AT Internal Program | N/A - AT internal governance | The *organizational* procedure for tracking and ensuring compliance with all legal/regulatory requirements. | Procedure Document | N/A | Incomplete | Before Project Starts | CSMS-001 | This is the *organizational* procedure. COMP-REG artifacts are the *outputs*.
68 | Program Management | 2025-12-12 | No | NCC - to compose Handover document to AT, as Responsible Party | AT | CSMS Documentation Management Procedure | CSMS - Program Management | CSMS-025 | CSMS Documentation Management Procedure | IEC 62443-2-1 | Low | Asset Owner (AT) | Asset Owner (AT) |  |  | Asset Owner (AT) - Establishes | Not Handed Over - AT Internal Program | N/A - AT internal governance | The *organizational* procedure for controlling all CSMS documentation. | Procedure Document | ISO 27001 A.7.5 | Incomplete | Before Project Starts | CSMS-001 | Defines how all other CSMS documents are managed.
69 | Development | 2025-01-15 | No | Provided via Supplier ,NCC - to reference in Cyber Security Management Plan | Supplier | Security Management Process (Supplier) | Secure Development- Product Supplier | S-DEV-4-1-001 | Security Management Process (Supplier) | IEC 62443-4-1 SM-1 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) - Executes | SI (Link Alliance) | Review as part of supplier assessment (DES-2-4-001) | Supplier provides evidence of a documented security management process for product development. | Policy/Procedure Document | ISO 27001 | N/A - Supplier Internal | Design Phase | DES-2-4-001 | This is an internal *process* document from the Supplier (Honeywell), requested by the SI as evidence for DES-2-4-001.
70 | Development | 2025-12-30 | No | Provided via Supplier ,NCC - to reference in Cyber Security Management Plan | Supplier | Security Requirements Definition | Secure Development- Product Supplier | S-DEV-4-1-002 | Security Requirements Definition | IEC 62443-4-1 SR-1 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) - Executes | SI (Link Alliance) | Review as part of supplier assessment (DES-2-4-001) | Supplier provides evidence of a documented process for defining security requirements for their products. | Policy/Procedure Document | N/A | N/A - Supplier Internal | Design Phase | DES-2-4-001 | This is an internal *process* document from the Supplier (Honeywell), requested by the SI as evidence for DES-2-4-001.
71 | Development | 2025-12-30 | No | Provided via Supplier ,NCC - to reference in Cyber Security Management Plan | Supplier | Secure Design Process | Secure Development- Product Supplier | S-DEV-4-1-003 | Secure Design Process | IEC 62443-4-1 SD-1 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) - Executes | SI (Link Alliance) | Review as part of supplier assessment (DES-2-4-001) | Supplier provides evidence of a documented secure design process (e.g., threat modeling). | Policy/Procedure Document | N/A | N/A - Supplier Internal | Design Phase | DES-2-4-001 | This is an internal *process* document from the Supplier (Honeywell), requested by the SI as evidence for DES-2-4-001.
72 | Development | 2025-12-30 | No | Provided via Supplier ,NCC - to reference in Cyber Security Management Plan | Supplier | Secure Implementation Process | Secure Development- Product Supplier | S-DEV-4-1-004 | Secure Implementation Process | IEC 62443-4-1 SI-1 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) - Executes | SI (Link Alliance) | Review as part of supplier assessment (DES-2-4-001) | Supplier provides evidence of a documented secure implementation process (e.g., coding standards). | Policy/Procedure Document | N/A | N/A - Supplier Internal | Design Phase | DES-2-4-001 | This is an internal *process* document from the Supplier (Honeywell), requested by the SI as evidence for DES-2-4-001.
73 | Development | 2025-12-30 | No | Provided via Supplier ,NCC - to reference in Cyber Security Management Plan | Supplier | Secure Verification and Validation (V&V) Process | Secure Development- Product Supplier | S-DEV-4-1-005 | Secure Verification and Validation (V&V) Process | IEC 62443-4-1 SVV-1 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) - Executes | SI (Link Alliance) | Review as part of supplier assessment (DES-2-4-001) | Supplier provides evidence of a documented V&V process (e.g., security testing) for their products. | Policy/Procedure Document | N/A | N/A - Supplier Internal | Design Phase | DES-2-4-001 | This is an internal *process* document from the Supplier (Honeywell), requested by the SI as evidence for DES-2-4-001.
74 | Development | 2025-12-30 | No | Provided via Supplier ,NCC - to reference in Cyber Security Management Plan | Supplier | Defect Management Process | Secure Development- Product Supplier | S-DEV-4-1-006 | Defect Management Process | IEC 62443-4-1 DM-1 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) - Executes | SI (Link Alliance) | Review as part of supplier assessment (DES-2-4-001) | Supplier provides evidence of a documented process for managing security defects. | Policy/Procedure Document | N/A | N/A - Supplier Internal | Design Phase | DES-2-4-001 | This is an internal *process* document from the Supplier (Honeywell), requested by the SI as evidence for DES-2-4-001.
75 | Development | 2025-12-30 | No | Provided via Supplier ,NCC - to reference in Cyber Security Management Plan | Supplier | Patch Management Process (Supplier) | Secure Development- Product Supplier | S-DEV-4-1-007 | Patch Management Process (Supplier) | IEC 62443-4-1 PM-1 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) - Executes | SI (Link Alliance) | Review as part of supplier assessment (DES-2-4-001) | Supplier provides evidence of a documented process for managing and securely delivering patches. | Policy/Procedure Document | N/A | N/A - Supplier Internal | Design Phase | DES-2-4-001 | This is an internal *process* document from the Supplier (Honeywell), requested by the SI as evidence for DES-2-4-001.
76 | Development | 2025-12-30 | No | Provided via Supplier ,NCC - to reference in Cyber Security Management Plan | Supplier | Product End-of-Life (EOL) Policy | Secure Development- Product Supplier | S-DEV-4-1-008 | Product End-of-Life (EOL) Policy | IEC 62443-4-1 EOL-1 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) - Executes | SI (Link Alliance) | Review as part of supplier assessment (DES-2-4-001) | Supplier provides their public-facing policy for product EOL and security support. | Policy Document | N/A | N/A - Supplier Internal | Design Phase | DES-2-4-001 | This is an internal *process* document from the Supplier (Honeywell), requested by the SI as evidence for DES-2-4-001.
77 | Development | 2025-12-30 | No | Provided via Supplier ,NCC - to reference in Cyber Security Management Plan | Supplier | Security Requirements Specification (per product) | Secure Development- Product Supplier | S-DEV-4-1-009 | Security Requirements Specification (per product) | IEC 62443-4-1 SR-2 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) - Creates | SI (Link Alliance) | Review of component documentation | Supplier provides a document stating the security requirements for a specific product. | Technical Document | N/A | N/A - Supplier Internal | Design Phase | DES-2-4-001 | This is *component-level* documentation provided by the Supplier (Honeywell). Serves as *input* to SI's CSRS (RA-3-2-005).
78 | Development | 2025-12-30 | No | Provided via Supplier ,NCC - to reference in Cyber Security Management Plan | Supplier | Product Threat Model | Secure Development- Product Supplier | S-DEV-4-1-010 | Product Threat Model | IEC 62443-4-1 SD-3 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) - Creates | SI (Link Alliance) | Review of component documentation (if provided) | Supplier may provide a high-level threat model or summary for a product. | Technical Document | N/A | N/A - Supplier Internal | Design Phase | DES-2-4-001 | This is *component-level* documentation provided by the Supplier (Honeywell). Serves as *input* to SI's Risk Assessment (RA-3-2-004).
79 | Development | 2025-12-30 | No | Provided via Supplier ,NCC - to reference in Cyber Security Management Plan | Supplier | Product Security Architecture Specification | Secure Development- Product Supplier | S-DEV-4-1-011 | Product Security Architecture Specification | IEC 62443-4-1 SD-4 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) - Creates | SI (Link Alliance) | Review of component documentation | Supplier provides documentation on the product's security architecture. | Technical Document | N/A | N/A - Supplier Internal | Design Phase | DES-2-4-001 | This is *component-level* documentation provided by the Supplier (Honeywell). Serves as *input* to SI's HLD (DES-3-3-001).
80 | Development | 2025-12-30 | No | Provided via Supplier ,NCC - to reference in Cyber Security Management Plan | Supplier | Secure Coding Standards | Secure Development- Product Supplier | S-DEV-4-1-012 | Secure Coding Standards | IEC 62443-4-1 SI-2 | Medium | Supplier (Honeywell) | Supplier (Honeywell) |  |  | Supplier (Honeywell) - Maintains | N/A - Internal Only | N/A - Internal Supplier Process | N/A - Not a project deliverable. | Internal Policy | N/A | N/A - Supplier Internal | N/A | DES-2-4-001 | This is a Supplier *internal-only* process document. The SI would not ask for this, only that a *process exists* (S-DEV-4-1-004).
81 | Development | 2025-12-30 | No | Provided via Supplier ,NCC - to reference in Cyber Security Management Plan | Supplier | Security Test (V&V) Plan | Secure Development- Product Supplier | S-DEV-4-1-013 | Security Test (V&V) Plan | IEC 62443-4-1 SVV-2 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) - Creates | SI (Link Alliance) | Review of component documentation (if provided) | Supplier provides evidence of their V&V test plan for a product. | Technical Document | N/A | N/A - Supplier Internal | Design Phase | DES-2-4-001 | This is *component-level* documentation provided by the Supplier (Honeywell). Serves as *input* to SI's Test Plans (TEST-3-3-001).
82 | Development | 2025-12-30 | No | Provided via Supplier ,NCC - to reference in Cyber Security Management Plan | Supplier | Security Test (V&V) Results | Secure Development- Product Supplier | S-DEV-4-1-014 | Security Test (V&V) Results | IEC 62443-4-1 SVV-4 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) - Creates | SI (Link Alliance) | Review of component documentation (if provided) | Supplier provides a summary of security test results for a product. | Test Report | N/A | N/A - Supplier Internal | Design Phase | DES-2-4-001 | This is *component-level* documentation provided by the Supplier (Honeywell). Serves as *input* to SI's Test Reports (TEST-3-3-001).
83 | Development | 2025-12-30 | No | Provided via Supplier ,NCC - to reference in Cyber Security Management Plan | Supplier | Vulnerability Response Plan (Supplier) | Secure Development- Product Supplier | S-DEV-4-1-015 | Vulnerability Response Plan (Supplier) | IEC 62443-4-1 DM-3 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) - Creates | SI (Link Alliance) | Review as part of supplier assessment (DES-2-4-001) | Supplier provides their public-facing plan/policy for handling vulnerability reports. | Policy Document | N/A | N/A - Supplier Internal | Design Phase | DES-2-4-001 | This is an internal *process* document from the Supplier (Honeywell), requested by the SI as evidence for DES-2-4-001.
84 | Development | 2025-12-30 | No | Provided via Supplier ,NCC - to reference in Cyber Security Management Plan | Supplier | Security Patch Release Notes | Secure Development- Product Supplier | S-DEV-4-1-016 | Security Patch Release Notes | IEC 62443-4-1 PM-3 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | Operator (Maintenance SP) | Asset Owner (AT) | Supplier (Honeywell) - Creates | Operator (Maintenance SP) | N/A - Ongoing operational artifact | Supplier provides clear release notes, including security impact, with every patch. | Release Notes | N/A | Ongoing | Ongoing | MAINT-PATCH-001 | This is an *ongoing* deliverable from the Supplier (Honeywell) to the Operator during the Maintenance phase.
85 | Development | 2025-12-30 | No | Provided via Supplier ,NCC - to reference in Cyber Security Management Plan | Supplier | Security Guideline Documents (Component) | Secure Development- Product Supplier | S-DEV-4-1-017 | Security Guideline Documents (Component) | IEC 62443-4-1 PM-5 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) - Creates | SI (Link Alliance) | Review of component documentation | Supplier provides security guidelines for their product (e.g., hardening, secure use). | Manual / Guide | N/A | N/A - Supplier Internal | Design Phase | DES-2-4-001 | This is *component-level* documentation (e.g., manual) provided by the Supplier (Honeywell). Serves as *input* to SI's DLD (DES-3-3-003).
86 | Development | 2025-12-30 | No | Provided via Supplier ,NCC - to reference in Cyber Security Management Plan | Supplier | Software Bill of Materials (SBOM) | Secure Development- Product Supplier | S-DEV-4-1-018 | Software Bill of Materials (SBOM) | IEC 62443-4-1 SI-1 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) - Creates | SI (Link Alliance) | Review of component documentation | Supplier provides an SBOM for their product, listing all open-source and third-party components. | SPDX/CycloneDX file | N/A | N/A - Supplier Internal | Design Phase | DES-2-4-001 | This is *component-level* documentation provided by the Supplier (Honeywell). Serves as *input* to SI's Risk Assessment (RA-3-2-004).
87 | Development | 2025-12-30 | No | Provided via Supplier ,NCC - to reference in Cyber Security Management Plan | Supplier | Development Environment Security Plan | Secure Development- Product Supplier | S-DEV-4-1-019 | Development Environment Security Plan | IEC 62443-4-1 SM-6 | Medium | Supplier (Honeywell) | Supplier (Honeywell) |  |  | Supplier (Honeywell) - Maintains | N/A - Internal Only | N/A - Internal Supplier Process | N/A - Not a project deliverable. | Internal Policy | N/A | N/A - Supplier Internal | N/A | DES-2-4-001 | This is a Supplier *internal-only* process document. The SI would not ask for this, only that a *process exists*.
88 | Development | 2025-12-30 | No | Provided via Supplier ,NCC - to reference in Cyber Security Management Plan | Supplier | Supply Chain Security Assessment | Secure Development- Product Supplier | S-DEV-4-1-020 | Supply Chain Security Assessment | IEC 62443-4-1 SM-7 | Medium | Supplier (Honeywell) | Supplier (Honeywell) |  |  | Supplier (Honeywell) - Maintains | N/A - Internal Only | N/A - Internal Supplier Process | N/A - Not a project deliverable. | Internal Records | N/A | N/A - Supplier Internal | N/A | DES-2-4-001 | This is a Supplier *internal-only* process. The SI would not ask for this, only that a *process exists*.
89 | Development | 2025-12-30 | No | Provided via Supplier ,NCC - to reference in Cyber Security Management Plan | Supplier | Third-Party Component Analysis | Secure Development- Product Supplier | S-DEV-4-1-021 | Third-Party Component Analysis | IEC 62443-4-1 SM-8 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) - Creates | SI (Link Alliance) | Review of component documentation (if provided) | Supplier provides evidence of analyzing third-party components (e.g., results from SBOM scan). | Internal Records | N/A | N/A - Supplier Internal | Design Phase | DES-2-4-001 | This is *component-level* documentation provided by the Supplier (Honeywell). Serves as *input* to SI's Risk Assessment (RA-3-2-004).
90 | Development | 2025-12-30 | No | Provided via Supplier ,NCC - to reference in Cyber Security Management Plan | Supplier | Security Training Records (Supplier) | Secure Development- Product Supplier | S-DEV-4-1-022 | Security Training Records (Supplier) | IEC 62443-4-1 SM-4 | Medium | Supplier (Honeywell) | Supplier (Honeywell) |  |  | Supplier (Honeywell) - Maintains | N/A - Internal Only | N/A - Internal Supplier Process | N/A - Not a project deliverable. | Internal Records | N/A | N/A - Supplier Internal | N/A | DES-2-4-001 | This is a Supplier *internal-only* process document. The SI would not ask for this, only that a *process exists*.
91 | Development | 2025-12-30 | No | Provided via Supplier ,NCC - to reference in Cyber Security Management Plan | Supplier | Periodic SDL Review Reports | Secure Development- Product Supplier | S-DEV-4-1-023 | Periodic SDL Review Reports | IEC 62443-4-1 SM-3 | Medium | Supplier (Honeywell) | Supplier (Honeywell) |  |  | Supplier (Honeywell) - Maintains | N/A - Internal Only | N/A - Internal Supplier Process | N/A - Not a project deliverable. | Internal Records | N/A | N/A - Supplier Internal | N/A | DES-2-4-001 | This is a Supplier *internal-only* process document. The SI would not ask for this, only that a *process exists*.
92 | Development | 2025-12-30 | No | Provided via Supplier ,NCC - to reference in Cyber Security Management Plan | Supplier | Continuous Improvement Plans (Supplier) | Secure Development- Product Supplier | S-DEV-4-1-024 | Continuous Improvement Plans (Supplier) | IEC 62443-4-1 SM-2 | Medium | Supplier (Honeywell) | Supplier (Honeywell) |  |  | Supplier (Honeywell) - Maintains | N/A - Internal Only | N/A - Internal Supplier Process | N/A - Not a project deliverable. | Internal Records | N/A | N/A - Supplier Internal | N/A | DES-2-4-001 | This is a Supplier *internal-only* process document. The SI would not ask for this, only that a *process exists*.
93 | Development | 2025-12-30 | No | Provided via Supplier ,NCC - to reference in Cyber Security Management Plan | Supplier | Product Discontinuation Notice | Secure Development- Product Supplier | S-DEV-4-1-025 | Product Discontinuation Notice | IEC 62443-4-1 EOL-2 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | Operator (Maintenance SP) | Asset Owner (AT) | Supplier (Honeywell) - Creates | Operator (Maintenance SP) | N/A - Ongoing operational artifact | Supplier provides formal notice of product discontinuation per their EOL policy. | Notice / Bulletin | N/A | Ongoing | Ongoing | MAINT-2-4-001 | This is an *ongoing* deliverable from the Supplier (Honeywell) to the Operator during the Maintenance phase.
94 | Development | 2025-12-30 | No | Provided via Supplier ,NCC - to reference in Cyber Security Management Plan | Supplier | Security Response Team (PSIRT) Charter | Secure Development- Product Supplier | S-DEV-4-1-026 | Security Response Team (PSIRT) Charter | IEC 62443-4-1 DM-2 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) - Creates | SI (Link Alliance) | Review as part of supplier assessment (DES-2-4-001) | Supplier provides evidence of an established PSIRT. | Policy Document / Webpage | N/A | N/A - Supplier Internal | Design Phase | DES-2-4-001 | This is an internal *process* document from the Supplier (Honeywell), requested by the SI as evidence for DES-2-4-001.
95 | Development | 2025-12-30 | No | Provided via Supplier ,NCC - to reference in Cyber Security Management Plan | Supplier | Use of Approved Tools/Compilers | Secure Development- Product Supplier | S-DEV-4-1-027 | Use of Approved Tools/Compilers | IEC 62443-4-1 SI-3 | Medium | Supplier (Honeywell) | Supplier (Honeywell) |  |  | Supplier (Honeywell) - Maintains | N/A - Internal Only | N/A - Internal Supplier Process | N/A - Not a project deliverable. | Internal Policy | N/A | N/A - Supplier Internal | N/A | DES-2-4-001 | This is a Supplier *internal-only* process document. The SI would not ask for this, only that a *process exists*.
96 | Development | 2025-12-30 | No | Provided via Supplier ,NCC - to reference in Cyber Security Management Plan | Supplier | Static/Dynamic Analysis Tools | Secure Development- Product Supplier | S-DEV-4-1-028 | Static/Dynamic Analysis Tools | IEC 62443-4-1 SVV-3 | Medium | Supplier (Honeywell) | Supplier (Honeywell) |  |  | Supplier (Honeywell) - Maintains | N/A - Internal Only | N/A - Internal Supplier Process | N/A - Not a project deliverable. | Internal Policy | N/A | N/A - Supplier Internal | N/A | DES-2-4-001 | This is a Supplier *internal-only* process document. The SI would not ask for this, only that a *process exists*.
97 | Development | 2025-12-30 | No | Provided via Supplier ,NCC - to reference in Cyber Security Management Plan | Supplier | Security Update Management Plan | Secure Development- Product Supplier | S-DEV-4-1-029 | Security Update Management Plan | IEC 62443-4-1 PM-2 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) - Creates | SI (Link Alliance) | Review as part of supplier assessment (DES-2-4-001) | Supplier provides their plan for how security updates are developed, tested, and distributed. | Policy Document | N/A | N/A - Supplier Internal | Design Phase | DES-2-4-001 | This is an internal *process* document from the Supplier (Honeywell), requested by the SI as evidence for DES-2-4-001.
98 | Component | 2025-12-12 | No | Provided via Supplier. Occurs via V&V - What is the defined process? | Supplier | Component Security Specification | Component Certification- Product Supplier | COMP-CERT-4-2-001 | Component Security Specification | IEC 62443-4-2 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) - Creates | SI (Link Alliance) | Review of component documentation | Supplier provides a document stating the security capabilities of a specific component. | Technical Document | N/A | N/A - Supplier Internal | Design Phase | DES-2-4-001 | This is *component-level* documentation provided by the Supplier (Honeywell). Serves as *input* to SI's CSRS (RA-3-2-005).
99 | Component | 2025-12-12 | No | Provided via Supplier. Occurs via V&V - What is the defined process? | Supplier | Component Requirements (CR) Compliance Matrix | Component Certification- Product Supplier | COMP-CERT-4-2-002 | Component Requirements (CR) Compliance Matrix | IEC 62443-4-2 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) - Creates | SI (Link Alliance) | Review of component documentation (if provided) | Supplier provides a matrix showing how their component meets 62443-4-2 requirements. | Technical Document | N/A | N/A - Supplier Internal | Design Phase | DES-2-4-001 | This is *component-level* documentation provided by the Supplier (Honeywell). Can be part of a formal certificate.
100 | Component | 2025-12-12 | No | Provided via Supplier. Occurs via V&V - What is the defined process? | Supplier | Device Type Classification | Component Certification- Product Supplier | COMP-CERT-4-2-003 | Device Type Classification | IEC 62443-4-2 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) - Creates | SI (Link Alliance) | Review of component documentation | Supplier provides a classification for their device (e.g., 'Embedded Device', 'Host Device'). | Technical Document | N/A | N/A - Supplier Internal | Design Phase | DES-2-4-001 | This is *component-level* documentation provided by the Supplier (Honeywell).
101 | Component | 2025-12-12 | No | Provided via Supplier. Occurs via V&V - What is the defined process? | Supplier | SL-C (Capability) Declaration | Component Certification- Product Supplier | COMP-CERT-4-2-004 | SL-C (Capability) Declaration | IEC 62443-4-2 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) - Creates | SI (Link Alliance) | Review of component documentation or certificate | Supplier provides a formal declaration of the Security Level (SL) their component is *capable* of achieving. | Certificate / Declaration | ISASecure | N/A - Supplier Internal | Design Phase | DES-2-4-001 | This is a key *component-level* document from the Supplier (Honeywell). It is a critical *input* to the SI's DLD.
102 | Component | 2025-12-12 | No | Provided via Supplier. Occurs via V&V - What is the defined process? | Supplier | Security Test Report (Component) | Component Certification- Product Supplier | COMP-CERT-4-2-005 | Security Test Report (Component) | IEC 62443-4-2 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) - Creates | SI (Link Alliance) | Review of component documentation (if provided) | Supplier provides security test reports for the component (e.g., vulnerability scan, fuzz testing). | Test Report | N/A | N/A - Supplier Internal | Design Phase | DES-2-4-001 | This is *component-level* documentation provided by the Supplier (Honeywell). Serves as *input* to SI's Test Plans (TEST-3-3-001).
103 | Component | 2025-12-12 | No | Provided via Supplier. Occurs via V&V - What is the defined process? | Supplier | Component Security Assurance Report | Component Certification- Product Supplier | COMP-CERT-4-2-006 | Component Security Assurance Report | IEC 62443-4-2 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) - Creates | SI (Link Alliance) | Review of component documentation or certificate | Supplier provides a formal report (e.g., from ISASecure) certifying the component. | Certificate / Report | ISASecure | N/A - Supplier Internal | Design Phase | DES-2-4-001 | This is a formal *component-level* certificate from the Supplier (Honeywell).
104 | Component | 2025-12-12 | No | Provided via Supplier. Occurs via V&V - What is the defined process? | Supplier | Vulnerability Assessment Report (Component) | Component Certification- Product Supplier | COMP-CERT-4-2-007 | Vulnerability Assessment Report (Component) | IEC 62443-4-2 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) - Creates | SI (Link Alliance) | Review of component documentation (if provided) | Supplier provides vulnerability reports for the component. | Test Report | N/A | N/A - Supplier Internal | Design Phase | DES-2-4-001 | This is *component-level* documentation provided by the Supplier (Honeywell). Serves as *input* to SI's Risk Assessment (RA-3-2-004).
105 | Component | 2025-12-12 | No | Provided via Supplier. Occurs via V&V - What is the defined process? | Supplier | Known Vulnerabilities List | Component Certification- Product Supplier | COMP-CERT-4-2-008 | Known Vulnerabilities List | IEC 62443-4-2 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) - Maintains | SI (Link Alliance) | Review of component documentation | Supplier provides a list of known vulnerabilities in the component at the time of shipping. | Technical Document | N/A | N/A - Supplier Internal | Design Phase | DES-2-4-001 | This is *component-level* documentation provided by the Supplier (Honeywell). Serves as *input* to SI's Risk Assessment (RA-3-2-004).
106 | Component | 2025-12-12 | No | Provided via Supplier. Occurs via V&V - What is the defined process? | Supplier | Security Update History (Component) | Component Certification- Product Supplier | COMP-CERT-4-2-009 | Security Update History (Component) | IEC 62443-4-2 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) - Maintains | SI (Link Alliance) | Review of component documentation | Supplier provides a history of security updates for the component. | Release Notes | N/A | N/A - Supplier Internal | Design Phase | DES-2-4-001 | This is *component-level* documentation provided by the Supplier (Honeywell).
107 | Component | 2025-12-12 | No | Provided via Supplier. Occurs via V&V - What is the defined process? | Supplier | Component Configuration Guide | Component Certification- Product Supplier | COMP-CERT-4-2-010 | Component Configuration Guide | IEC 62443-4-2 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) - Creates | SI (Link Alliance) | Review of component documentation | Supplier provides the standard configuration guide for the component. | Manual / Guide | N/A | N/A - Supplier Internal | Design Phase | DES-2-4-001 | This is *component-level* documentation provided by the Supplier (Honeywell). Serves as *input* to SI's DLD (DES-3-3-003).
108 | Component | 2025-12-12 | No | Provided via Supplier. Occurs via V&V - What is the defined process? | Supplier | Secure Deployment Guide (Component) | Component Certification- Product Supplier | COMP-CERT-4-2-011 | Secure Deployment Guide (Component) | IEC 62443-4-2 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) - Creates | SI (Link Alliance) | Review of component documentation | Supplier provides a guide on how to securely *deploy* the component. | Manual / Guide | N/A | N/A - Supplier Internal | Design Phase | DES-2-4-001 | This is *component-level* documentation provided by the Supplier (Honeywell). Serves as *input* to SI's DLD (DES-3-3-003).
109 | Component | 2025-12-12 | No | Provided via Supplier. Occurs via V&V - What is the defined process? | Supplier | Security Hardening Guide (Component) | Component Certification- Product Supplier | COMP-CERT-4-2-012 | Security Hardening Guide (Component) | IEC 62443-4-2 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) - Creates | SI (Link Alliance) | Review of component documentation | Supplier provides a guide on how to *harden* the component's configuration. | Manual / Guide | CIS Benchmarks | N/A - Supplier Internal | Design Phase | DES-2-4-001 | This is *component-level* documentation provided by the Supplier (Honeywell). Serves as *input* to SI's DLD (DES-3-3-003).
110 | Component | 2025-12-12 | No | Provided via Supplier. Occurs via V&V - What is the defined process? | Supplier | Component User Manual (Security) | Component Certification- Product Supplier | COMP-CERT-4-2-013 | Component User Manual (Security) | IEC 62443-4-2 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) - Creates | SI (Link Alliance) | Review of component documentation | Supplier provides the user manual, which must include security features. | Manual / Guide | N/A | N/A - Supplier Internal | Design Phase | DES-2-4-001 | This is *component-level* documentation provided by the Supplier (Honeywell). Serves as *input* to SI's Training (HO-2-1-003).
111 | Component | 2025-12-12 | No | Provided via Supplier. Occurs via V&V - What is the defined process? | Supplier | Administrator Security Guide (Component) | Component Certification- Product Supplier | COMP-CERT-4-2-014 | Administrator Security Guide (Component) | IEC 62443-4-2 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) - Creates | SI (Link Alliance) | Review of component documentation | Supplier provides a specific guide for administrators on component security. | Manual / Guide | N/A | N/A - Supplier Internal | Design Phase | DES-2-4-001 | This is *component-level* documentation provided by the Supplier (Honeywell). Serves as *input* to SI's DLD (DES-3-3-003) and Training (HO-2-1-003).
112 | Component | 2025-12-12 | No | Provided via Supplier. Occurs via V&V - What is the defined process? | Supplier | Security Capabilities Statement | Component Certification- Product Supplier | COMP-CERT-4-2-015 | Security Capabilities Statement | IEC 62443-4-2 | Medium | Supplier (Honeywell) | Supplier (Honeywell) | SI (Link Alliance) | Asset Owner (AT) | Supplier (Honeywell) - Creates | SI (Link Alliance) | Review of component documentation | Supplier provides a high-level summary of the component's security features. | Technical Document | N/A | N/A - Supplier Internal | Design Phase | DES-2-4-001 | This is *component-level* documentation provided by the Supplier (Honeywell).
113 | Compliance | 2025-11-30 | No |  | NCC | Security Case | Compliance - Security Case | SEC-CASE-001 | Security Case Plan | N/A | High | SI (Link Alliance) | Asset Owner (AT) | Operator (Maintenance SP) |  | SI (Link Alliance) - Creates plan ¦ Asset Owner (AT) - Approves | SI (Link Alliance) | Review and approval of the plan by AT. | Plan details the scope, methodology, schedule, and responsibilities for developing the complete Security Case. | Project Plan Document | RSNL, NZISM | Incomplete | Design Phase | RA-3-2-005, COMP-REG-002 | The *plan* for how the SI will prove the system is secure and meets all RSNL and NZISM requirements.
114 | Compliance | 2025-11-30 | No |  | NCC | Security Case | Compliance - Security Case | SEC-CASE-002 | Security Case Strategy | N/A | High | SI (Link Alliance) | Asset Owner (AT) | Operator (Maintenance SP) |  | SI (Link Alliance) - Creates strategy ¦ Asset Owner (AT) - Approves | SI (Link Alliance) | Review and approval of the strategy by AT. | Strategy defines the argument structure (e.g., Goal Structuring Notation) that will be used to link evidence to claims. | Strategy Document | RSNL, NZISM | Incomplete | Design Phase | SEC-CASE-001 | The high-level *argument* for why the system is secure, which the rest of the case will prove.
115 | Compliance | 2025-12-12 | No |  | NCC | Security Case | Compliance - Security Case | SEC-CASE-003 | Hazard and Risk Analysis (Security) | N/A | High | SI (Link Alliance) | Asset Owner (AT) | Operator (Maintenance SP) |  | SI (Link Alliance) - Executes ¦ Asset Owner (AT) - Approves | SI (Link Alliance) | Review and approval of risk analysis. | This artifact is the formal risk assessment (RA-3-2-004) re-framed as the primary input for the Security Case. Must be aligned with RSNL. | Risk Assessment Report | RSNL, ISO 27005 | Incomplete | Risk Assessment | RA-3-2-004, COMP-REG-002 | This is the core risk analysis (RA-3-2-004) that feeds the safety/security case.
116 | Compliance | 2025-12-12 | No |  | NCC | Security Case | Compliance - Security Case | SEC-CASE-004 | Security Requirements (Derived) | N/A | High | SI (Link Alliance) | Asset Owner (AT) | Operator (Maintenance SP) |  | SI (Link Alliance) - Authors ¦ Asset Owner (AT) - Approves | SI (Link Alliance) | Review and approval of requirements. | This artifact is the CSRS (RA-3-2-005) framed as the set of controls mitigating risks identified in SEC-CASE-003. | Requirements Specification Document | IEC 62443-3-3, RSNL | Incomplete | Risk Assessment | RA-3-2-005, SEC-CASE-003 | This is the core requirements list (RA-3-2-005) that must be proven as implemented.
117 | Compliance | 2025-01-15 | No | NCC -Security Case - Will refer as "interim" at Jan 15, After V&V sampling is completed on actuals, will update to "Final" | NCC | Security Case | Compliance - Security Case | SEC-CASE-005 | Security Case Evidence Package | N/A | High | SI (Link Alliance) | Asset Owner (AT) | Operator (Maintenance SP) |  | SI (Link Alliance) - Compiles ¦ Asset Owner (AT) - Accepts | SI (Link Alliance) | Review and audit of all referenced evidence. | A compiled package of all objective evidence (DLDs, test reports, scan results, etc.) mapped to requirements (SEC-CASE-004). | Document / Data Package | N/A | Incomplete | Handover Phase | All DES, IMPL, TEST artifacts | This is the body of evidence. It contains all the project deliverables (DLDs, TEST-3-3-002, etc.).
118 | Compliance | 2025-01-15 | No | NCC -Security Case - Will refer as "interim" at Jan 15, After V&V sampling is completed on actuals, will update to "Final" | NCC | Security Case | Compliance - Security Case | SEC-CASE-006 | Security Case Argument | N/A | High | SI (Link Alliance) | Asset Owner (AT) | Operator (Maintenance SP) |  | SI (Link Alliance) - Authors ¦ Asset Owner (AT) - Accepts | SI (Link Alliance) | Formal review and acceptance of the argument. | The complete, formal argument (e.g., in GSN) linking the claims (SEC-CASE-002) to the requirements (SEC-CASE-004) and the evidence (SEC-CASE-005). | Report / GSN Diagram | N/A | Incomplete | Handover Phase | SEC-CASE-002, SEC-CASE-004, SEC-CASE-005 | This is the 'glue' that logically proves the case.
119 | Compliance | 2025-01-15 | No | NCC -Security Case - Will refer as "interim" at Jan 15, After V&V sampling is completed on actuals, will update to "Final" | NCC | Security Case | Compliance - Security Case | SEC-CASE-007 | Residual Risk Statement | N/A | High | SI (Link Alliance) | Asset Owner (AT) | Operator (Maintenance SP) |  | SI (Link Alliance) - Authors ¦ Asset Owner (AT) - Accepts | SI (Link Alliance) | Formal review and acceptance of residual risks by AT. | A formal statement of all residual risks (from RA-3-2-004) that are being transferred to the Asset Owner for acceptance. | Risk Register (Residual) | ISO 27005 | Incomplete | Handover Phase | RA-3-2-004, TEST-3-3-003 | The final risk register showing all accepted risks post-mitigation.
120 | Compliance | 2025-01-15 | No | NCC -Security Case - Will refer as "interim" at Jan 15, After V&V sampling is completed on actuals, will update to "Final" | NCC | Security Case | Compliance - Security Case | SEC-CASE-008 | Operational Limitations and Assumptions | N/A | High | SI (Link Alliance) | Asset Owner (AT) | Operator (Maintenance SP) |  | SI (Link Alliance) - Authors ¦ Asset Owner (AT) / Operator - Accept | SI (Link Alliance) | Review and acceptance by AT and Operator. | A clear list of all assumptions made in the design (e.g., 'physical security is handled by AT') and limitations for safe operation (e.g., 'Operator must patch quarterly'). | Procedure Document | N/A | Incomplete | Handover Phase | All DES, HO artifacts | Defines the operational boundaries and responsibilities the Operator *must* follow to maintain security.
121 | Compliance | 2025-01-15 | No | NCC -Security Case - Will refer as "interim" at Jan 15, After V&V sampling is completed on actuals, will update to "Final" | NCC | Security Case | Compliance - Security Case | SEC-CASE-009 | Security Case Summary Report | N/A | High | SI (Link Alliance) | Asset Owner (AT) | Operator (Maintenance SP) |  | SI (Link Alliance) - Authors ¦ Asset Owner (AT) - Signs off | SI (Link Alliance) | Formal sign-off by AT leadership. | A high-level executive summary of the entire Security Case, including the final argument (SEC-CASE-006) and residual risk (SEC-CASE-007). | Report | N/A | Incomplete | Handover Phase | SEC-CASE-006, SEC-CASE-007 | The final sign-off document for the project. This replaces the generic 'HO-FINAL-001'.

## Critical Items List
Lifecycle Phase | High-Priority SI Deliverable (Artifact_ID) | Critical Dependencies & Key Notes
Program Management | CSMS-001 (CSMS Plan) | Dependency: AO-2-1-001 (AT's Program).
SI-Note: We deliver the system-specific plan that AT adopts.
Program Management | CSMS-002 (CSMS Security Policy) | Dependency: AO-2-1-002 (AT's Policy).
SI-Note: We deliver the system-specific policy for AT to issue.
Program Management | CSMS-003 (Org. Structure & Responsibilities) | Dependency: CSMS-001.
SI-Note: We define the RACI for the CRL system (SI, AT, Operator).
Program Management | CSMS-004 (Risk Management Process) | Dependency: AO-2-1-003 (AT's RA Methodology).
SI-Note: This is our execution of AT's approved methodology.
Risk Assessment | RA-3-2-001 (High-Level Risk Assessment) | Dependency: AO-2-1-003 (AT's RA Methodology).
SI-Note: Establishes scope and boundaries.
Risk Assessment | RA-3-2-002 (Asset Inventory) | Dependency: Supplier component lists.
SI-Note: A living document, critical for all subsequent phases.
Risk Assessment | RA-3-2-003 (Zone and Conduit Definition) | Dependency: RA-3-2-001, RA-3-2-002, AO-2-1-004 (SL-T).
SI-Note: The foundational security architecture.
Risk Assessment | RA-3-2-004 (Detailed Cyber Risk Assessment) | Dependency: RA-3-2-003.
SI-Note: This is the core risk register that feeds the Security Case (SEC-CASE-003).
Risk Assessment | RA-3-2-005 (Cybersecurity Req's Spec - CSRS) | Dependency: RA-3-2-004.
SI-Note: Defines what we build. All requirements must be testable.
Design | DES-3-3-001 (High-Level Security Design - HLD) | Dependency: RA-3-2-005 (CSRS).
SI-Note: The conceptual "how" that traces to the "what" (CSRS).
Design | DES-3-3-002 (Detailed Security Design - DLD - Network) | Dependency: DES-3-3-001.
SI-Note: The build-to package for all network hardware (firewalls, etc.).
Design | DES-3-3-003 (Detailed Security Design - DLD - System) | Dependency: DES-3-3-001, COMP-CERT-4-2-012 (Hardening Guide).
SI-Note: The build-to package for servers, workstations, and controllers.
Implementation | IMPL-3-3-001 (System Build & Config Records) | Dependency: DES-3-3-002, DES-3-3-003.
SI-Note: The "as-built" records. Forms key evidence for the Security Case.
Implementation | IMPL-3-3-007 (Configuration Baselines) | Dependency: IMPL-3-3-001.
SI-Note: The "golden image" of the system at handover, used for future change management.
Implementation | IMPL-3-3-009 (Patch Management & AV Procedures) | Dependency: CSMS-012 (AT's Patch Plan).
SI-Note: The "how-to" guide for the Operator. Must be approved by Operator.
Testing | TEST-3-3-001 (FAT - Security) | Dependency: IMPL-3-3-001, RA-3-2-005 (CSRS).
SI-Note: Proves requirements are met in the lab. Test plan must trace to CSRS.
Testing | TEST-3-3-002 (SAT - Security) | Dependency: TEST-3-3-001.
SI-Note: Proves requirements are met on-site. The primary evidence for the Security Case.
Testing | TEST-3-3-003 (Vulnerability Scan Report) | Dependency: TEST-3-3-002.
SI-Note: A critical acceptance gate. All Critical/Highs must be remediated or risk-accepted by AT.
Compliance | COMP-REG-003 (NZISM Compliance Package) | Dependency: All DES, IMPL, TEST artifacts, SEC-CASE-009.
SI-Note: The formal package for government accreditation.
Compliance | SEC-CASE-001 to SEC-CASE-009 | Dependency: All artifacts in this table.
SI-Note: The complete set of compliance deliverables to achieve final sign-off.
Operations | HO-2-1-001 (Incident Response Plan - System) | Dependency: CSMS-005 (AT's Org. Plan).
SI-Note: The system-specific playbook for the Operator.
Operations | HO-2-1-002 (Disaster Recovery Plan - System) | Dependency: CSMS-006 (AT's Org. Plan), IMPL-3-3-006.
SI-Note: The system-specific bare-metal recovery guide for the Operator.
Operations | HO-FINAL-001 (Final Handover Package) | Dependency: SEC-CASE-009.
SI-Note: The final administrative compilation of all project documents for handover.